## BLTP
| Leap 4 Peace | Organisation: BLTP
Indicator Reporting Template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2025 (Totals Jan-Sept) | Description | Target 2025 | Explanation of deviation
LTO1 | Women are aware of the risk of not asserting their political rights | # women (aspiring) leaders trained | 209 | This target includes women members of nine new multi-party groups initiated in 2025 by the first groups formed in 2022 | 100 | Women members of the former VSLA have been dynamic and have initiated other groups. This is indeed a sustainable action, as these new groups have just benefited from revolving credit. This exceeds expectations, as only five new groups were expected.
| Women are able to put in place advocacy strategies | # agreements reached as a result of dialogue platform meeting | 1 | An agreement has been reached on the practical arrangements for supporting women candidates in the June 2025 parliamentary elections who are placed first, second and third on the list. This was the result of a three-level dialogue: first with the Ministry that manages political parties, then with the political parties that participated in the elections, and finally with the flexibility of the donor. This support was extended to women from all political parties involved in the elections, including those from the coalition of parties. | 2 | The discrepancy can be explained by the fact that it was not possible to influence the revision of the regulatory texts governing the elections, taking into account the new administrative division. In fact, an agreement was expected, notably on changing the number of senators following the reduction in the number of provinces. This was not possible, as the constitution provides for two senators per province and the co-opting of Batwa, while ensuring gender balance. Respect for the constitution took precedence over any agreement.
| Women are well represented in political decision-making processes | # of political actors who implement internal measures | 10 | The 10 parties supported have respected their commitments to better position women in the June 2025 elections. No party file has been rejected by the CENI for non-compliance with gender balance | 10 | No deviation
| Women politicians use the media to inform, educate and communicate their civil and political rights in general and their right to political participation in particular. | # political actors participating in dialogue platforms (disaggregated by type) | 5 | The five types of political actors strengthened are: i) The presidents of the election campaigns of all parties participating in the 2025 elections, ii) The women presidents of the parties participating in the 2025 parliamentary elections, iii) The presidents of the women's leagues of all parties participating in the elections, iv)Women candidates in parliamentary elections placed in the first, second and third positions on the party's electoral list approved by the CENI and v) the focal points of political parties. | 5 | No deviation
| Women politicians influence political and governmental decision makers | # interparty dialogue meetings | 4 | During this year, the multi-party dialogue meetings organised are: The exchange meeting with the presidents of political parties on the modalities of support for women candidates; The handover meeting between the first multi-party VSLA groups of 2022 and the new groups they initiated in 2025; Self-assessment of elections at provincial and national level; And a meeting with the various stakeholders to discuss the results achieved by the project. | 4 | No deviation
LTO2 | Government adopts policies that promote women's participation in decision-making bodies | Share of women candidates | 38.7% | This value refers to the results of the June 2025 parliamentary elections, as the BLTP took time to empower women to better prepare for elections, particularly parliamentary elections. | 35% | This is a step forward, as the proportion of women in parliament has increased.
| Government adopts practices that promote women's participation in decision-making bodies | Outcome harvesting
| Political parties adopt policies that promote women's participation in decision-making bodies | # political actors who adopt measures and policies to enhance representation of women in their decision-making processes | 2 | This refers to the CNL party, which did not hold an internal meeting following the suspension of its activities. As soon as the situation settled down with the appointment of a new leader, they carried out this activity. The other actor is the CNDD-FDD party, which said it agreed with the recommendations and commitments made by the other political parties, summarised in the document "Inclusion of women in politics". | 2 | No deviation
| Stronger and broader alliances are built between CSOs and women's political structures/organisations | Number of other CSOs and churches included in the programme activities | 2 | In addition to eight women's organisations, two other organisations, namely CICB (Interfaith Council of Burundi) and UNIPROBA (Let's Unite for the Protection of the Batwa), were added to the programme's activities. | 2 | No deviation

## NIMD_CO
| Leap 4 Peace | Organization: NIMD Colombia
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2025 (Totals Jan-Sept) | Description | Target 2025 | Explanation deviation
LTO1 | 1.2 Women nominate themselves for decision-making positions | # of women who partake in NIMD trainings that are willing to candidate themselves for decision-making positions | 0 | No target was set for this indicator by 2025, as the program achieved the overall goal | 0
| 1.3. Women increase their capabilities and abilities to partake in politics | # of women (aspiring) leaders trained | 0 | No target was set for this indicator by 2025, as the program achieved the overall goal | 0
| 1.3. Women increase their capabilities and abilities to partake in politics | # of democracy schools graduates | 0 | No target was set for this indicator by 2025, as the program achieved the overall goal | 0
| 2.1. Political actors implement internal gender-equality regulations | # political actors who implement internal measures and/or policies to enhance representation of women in their decision-making | 2 | With the support of the LEAP4Peace program in Colombia, as of September 2025, two political actors implemented measures that are part of their action plans: 1. Women’s Caucus of the Local Administrative Board of La Candelaria: As part of its action plan, which includes women’s political participation and advocacy in decision-making spaces as strategic priorities, the Caucus identified the need to strengthen its capacities in two main areas: First, in understanding and identifying violence against women in politics (VCMP), as well as knowledge and application of Law 2453 of 2025. On the other hand, in Political Oversight and Local Advocacy, which are fundamental for implementing the actions defined in their action plan, with a clear understanding of their scope and the tools available to the Caucus. NIMD Colombia conducted these trainings as technical support for the plan’s implementation. 2. Women’s Caucus of the Local Administrative Board of Bosa: As part of its action plan, which includes gender-based violence as a thematic focus, the Caucus identified the need to strengthen its capacity to understand and identify violence against women in politics (VCMP), as well as to understand and apply Law 2453 of 2025. NIMD Colombia conducted these training sessions as technical support for the plan’s implementation. The caucuses are a collegiate body at the local level. | 0 | There is a deviation from the goal set for 2025, given that the process initiated with the Women’s Caucus of the Local Administrative Boards of La Candelaria and Bosa continued, and they made progress in the implementation of their action plans. In both cases, the caucuses identified the need to strengthen their capacities on issues such as violence against women in politics (VCMP) and political oversight and local advocacy, which are key to continuing the actions defined in their plans, demonstrating the strengthening of women’s political leadership at the local level.
| 2.2. Political actors develop internal gender-equality regulations | # political actors who adopt internal measures and/or policies to enhance representation of women in their decision-making | 2 | In total, two political actors have developed internal measures on gender equality: 1. The Women’s Caucus of the Local Administrative Board of Bosa in the city of Bogotá developed its action plan with the support of NIMD Colombia and the District Secretariat for Women. 2. The Women’s Caucus of the Local Administrative Board of La Candelaria in the city of Bogotá developed its action plan with the support of NIMD Colombia and the District Secretariat for Women. The caucuses are collegiate bodies operating at the local level. *Clarification: The results of indicators IO 2.3 and 2.2 are not cumulative. The political actors involved are part of a multi-phase process that began in 2021 and is still ongoing. | 0 | There is a deviation from the target set for 2025, as work continued with the District Secretariat for Women to strengthen the capacities of the women’s caucuses.
| 2.3. Political actors assess their status on gender-equality | # political actors trained | 1 | As of September 2025, the LEAP4Peace program in Colombia had trained 1 political actor: . Dignidad y Compromiso Political Party: As part of the work of NIMD Colombia and the LEAP4Peace program within the District’s Multiparty Gender Roundtable, the Dignidad y Compromiso party recognizes the need to continue raising awareness and training its members regarding violence against women in politics, the response and disciplinary protocol developed by the political organization, and the implementation of Law 2453 of 2025. The training was attended by 14 people: 3 men and 11 women. Of the total number of people trained, 2 were 28 years old or younger, and 12 were 29 years old or older. *Clarification: the results of indicators IO 2.3 and 2.2 are not cumulative. The political actors involved are part of a process in different phases that began in 2021 and continues to unfold. | 0 | There is a deviation from the set target because the political actor identified and requested technical support from NIMD Colombia to review and improve internal measures, as well as public-facing actions, that promote gender equality. This situation stems from the processes that have unfolded during the implementation of the LEAP4Peace program within the Bogotá District Multiparty Gender Roundtable.
LTO2 | 3.1. Political actors jointly advocate for the implementation of gender-equality agenda | # of advocacy initiatives carried out by political actors | 1 | As of September 2025, one communications campaign was carried out by the Bogotá District Multiparty Gender Roundtable (MDMG) in the city of Bogotá: As part of its action plan and as a result of the meetings held, with technical support from NIMD Colombia, the Roundtable designed and implemented a communications strategy aimed at encouraging young women to run as candidates in the Local Youth Council elections. The strategy included informational materials about the electoral process, information on how to register for the elections through political parties, and a video featuring the voices of women from the parties, emphasizing the importance of increasing the presence and participation of young women in these spaces. This joint initiative was considered a priority, given that the elections are taking place this year, and its implementation contributes to increasing young women’s political participation and advancing the strategic objectives defined by the Roundtable. The District Multiparty Gender Roundtable is a multiparty forum at the local level that brings together delegates from 18 political parties with a presence in the city of Bogotá. | 0 | There is a deviation from the set goal, as during this period the District Multiparty Gender Roundtable’s Action Plan for 2025 was formulated. As part of this process, the Roundtable identified communications as one of its priority areas, from which a communications strategy was derived aimed at promoting the participation of young women as candidates in the elections for the Local Youth Councils. This demonstrates the Roundtable’s strengthened capacity to plan and implement actions that promote women’s political participation.
| 3.2. Political actors develop joint gender-equality agenda | # agreements reached as a result of dialogue platform meeting | 2 | Over the past five years, NIMD Colombia, through the LEAP4Peace program and in partnership with the District Secretariat for Women, has supported the District Multiparty Gender Roundtable in Bogotá. As a result of this work, two multiparty agreementswere reached in 2025 : During the Roundtable’s meetings, participants unanimously approved the guidelines for the functioning of this space for dialogue. Additionally, they consolidated and launched their Action Plan for 2025, a tool that structures the Roundtable’s actions and demonstrates the coordinated work among women from different parties. The plan includes three thematic areas: (1) Programming and Advocacy, (2) Knowledge Management, and (3) Communications. | 1 | There is a deviation from the original goal, as during this period the members of the District Multiparty Gender Roundtable (MDMG) decided that, for the successful implementation of their planned action plan, the rules governing this space for dialogue needed to be clearly established. Both agreements were reached thanks to the ongoing coordination efforts by NIMD Colombia and the District Secretariat for Women.
| 3.3. Political actors have a safe space for discussing gender-equality issues | # of political actors participating in dialogue platforms (disaggregated by type) | 155 | 155 political actors participated in dialogue forums, distributed as follows: 18 political parties and movements at the district level; 18 political parties and movements at the national level; 56 representatives of collegiate bodies (Municipal Councils and Departmental Assemblies); 43 representatives of the executive branch at the local level (mayors’ offices); 3 representatives of the executive branch at the departmental level (governors’ offices); and 17 representatives of the executive branch at the national level (ministries, agency directorates, units, administrative departments); and 13 members of Congress participated in the five multi-party dialogue forums, which will be detailed further in the following indicator. Broken down by total participants, 183 people were reported, of whom 19 at the national level are technical staff and 37 are high-level officials; at the departmental level, 35 are high-level officials; and at the local level, 18 are technical staff and 74 are high-level officials. *Clarification: the results of the IO 3.3 indicators are not cumulative. The political actors involved are part of a process in different phases in which they will continue to work, although new political actors may be added. | 8 (79) | Thanks to the sustained joint work with key entities such as the District Secretariat for Women and the Ministry of the Interior, the dialogue forums—which have brought together a wide range of political actors year after year around the agenda for the defense of women’s rights and the political participation of underrepresented groups—have continued. This process has been integrated and established through the interaction among these political actors, via the ongoing building of mutual trust and the consolidation of a common agenda.
| 3.3. Political actors have a safe space for discussing gender-equality issues | # interparty dialogue meetings | 5 | Building on the sustained work with the District Secretariat for Women, the Ministry of the Interior, and the Gender Roundtable on International Cooperation, with the aim of uniting coordinated efforts with political parties and movements in the city of Bogotá and the country, as of September 2025, five multiparty dialogue forumswere held , as follows: • 1 National Multiparty Women’s Roundtable: A total of 26 people from 18 different political parties and movements participated in this roundtable, comprising 7 high-level representatives and 19 technical-level representatives at the national level. This forum outlined the responsibilities involved in implementing Law 2453 of 2025 for political parties and state entities such as the Ministry of the Interior and the National Electoral Council. • 3 District-Level Multi-Party Gender Roundtables in Bogotá: A total of 25 women from 18 different political parties and movements participated in these three roundtables, comprising 7 high-level representatives and 18 technical-level representatives at the district level. During the meetings, participants discussed the committee’s operating guidelines, finalized the action plan for 2025, and agreed on activities related to the communications campaign. • 1 Summit of Women Leaders for Equality: A total of 132 political actors participated in this Summit, distributed as follows: 56 representatives of collegiate bodies (Municipal Councils and Departmental Assemblies); 43 representatives of the executive branch at the local level (mayors’ offices); 3 representatives of the executive branch at the departmental level (governors’ offices); 17 representatives of the executive branch at the national level (ministries, agency directorates, units, administrative departments); and 13 members of Congress. Nine political parties were represented at the event. The summit facilitated dialogue on the challenges female leaders face in various contexts across the country in exercising their political leadership. | 3 | Thanks to the sustained joint work with key entities such as the District Secretariat for Women and the Ministry of the Interior, the dialogue forums—which have brought together a wide range of political actors year after year around the agenda for the defense of women’s rights and the political participation of underrepresented groups—were continued. This process has been integrated and established within the interaction among these political actors through the ongoing building of mutual trust and the consolidation of a common agenda.
| 4.1 Women CSOs/Feminist movements effectively monitor and lobby for policy change and implementation | # of national advocacy initiatives carried out by CSOs | 0 | No target was set for this indicator by 2025, as the program achieved the overall goal | 0
| 4.2. Women CSOs/Feminist movements develop joint gender-equality agenda | # of multi-stakeholder dialogue/platform meetings | 2 | As of September 2025, two multi-stakeholder dialogue meetings had been held: These meetings took place as part of Phase 3 of the advocacy process aimed at involving women in the formulation and monitoring of public policies in the department of Meta, specifically in the municipalities of Guamal and Granada. During these sessions, women were given priority and were able to share their main concerns regarding women’s rights with local authorities; they agreed to continue this joint effort in future meetings. These meetings were held in partnership with the Women’s International League for Peace and Freedom (LIMPAL) Colombia. Forty-one social leaders and 13 political actors participated in these meetings, including female council members and representatives of the municipal and departmental governments. Fifty-four people participated in these meetings, broken down as follows: 40 women, 1 man, and 18 did not report their gender. By age, 46 are 29 years old or older, 5 are 28 years old or younger, and 4 did not report their age. *Note: Not all women reported their role, institutional affiliation, or age. | 0 | There is a deviation from the proposed target due to the work carried out in partnership with LIMPAL Colombia and directed at women’s organizations to advocate for the formulation and monitoring of public policies for women in their municipalities. This work was significantly expanded with the aim of continuing the previous advocacy work conducted in 2024 on Development Plans.
| 4.2. Women CSOs/Feminist movements develop joint gender-equality agenda | # studies for evidence-based L&A disseminated to political actors | 1 | As of September 2025, one (1) report was sharedjointly prepared by Transparencia por Colombia, the National Electoral Council (CNE), and NIMD Colombia, which compiles a compendium of best practices for political participation with a gender focus. The findings in this document stem from technical roundtables held in 2024, which aimed to identify barriers and compile best practices to strengthen equity in women’s political participation, with a focus on violence against women in politics. The document was shared with CNE officials to promote internal actions for the effective implementation of Law 2453 of 2025 on violence against women in politics. This report was produced as part of the work with the Observatory on Violence Against Women in Politics, which has monitored the prevalence of such violence in the country over the past five years. You can explore the report here: https://nimddenhaag.sharepoint.com/:b:/s/Colombia/EfEXQ8oLzTVPmbCVm-Xlt8gB_nrbLAFlLIh11TZ-MqPtRA?e=YeDRad | 1 (5)
| 4.3. Women CSOs/Feminist movements have capabilities for lobby and advocate political actors | # women led CSOs with increased L&A capacities | 67 | As of September 2025, NIMD Colombia has contributed to strengthening the lobbying and advocacy capacities of 67 women’s civil society organizations, which participated in an advocacy process regarding the formulation and monitoring of public policy for women in their municipalities, carried out in partnership with the Women’s International League for Peace and Freedom (LIMPAL Colombia), and, furthermore, in a process to develop joint advocacy agendas and localize the National Action Plan for the implementation of United Nations Security Council Resolution 1325, carried out in partnership with ICCO Conexión. In this regard, women’s organizations actively prepared to strengthen their capacities, formulate proposals, and monitor efforts to guarantee women’s rights and peace. The process carried out in partnership with LIMPAL unfolded in three phases in the departments of Bolívar, Meta, and Cauca. The process carried out in partnership with ICCO Conexión unfolded in two phases in Nariño and La Guajira. Of these 67 women’s civil society organizations, 36 are formal and 31 are informal. Explanatory notes: *We count as women’s civil society organizations those reported by women on the attendance list. It is important to note that there may be 1, 2, 3, or more women representatives from the same civil society organization. *The results of the IO 4.3 indicators are not cumulative. Civil society organizations (CSOs) led by the women involved are part of a multi-phase process in which they will continue to work. | 2 | There is a deviation from the proposed target, resulting from the work carried out in partnership with LIMPAL Colombia, aimed at strengthening the capacities of women’s organizations and their advocacy in the formulation and monitoring of public policies for women in their municipalities. This process was significantly expanded with the aim of ensuring continuity and building on the progress achieved in 2024 regarding advocacy on Territorial Development Plans. Additionally, the partnership established with ICCO Conexión expanded the scope of actions, enabling work with new women’s organizations to consolidate advocacy agendas regarding the National Action Plan for the implementation of United Nations Security Council Resolution 1325.
| 4.3. Women CSOs/Feminist movements have capabilities for lobby and advocate political actors | # of women led CSOs included in the programme activities | 67 | As of September 2025, NIMD Colombia has included a total of 67 women’s civil society organizations in its activities: As part of the working partnership with the Women’s International League for Peace and Freedom (LIMPAL)Colombia, representatives from 34 women’s civil society organizations participated in an advocacy process regarding the formulation and monitoring of public policies for women in their municipalities. This process unfolded in three phases in the departments of Cauca, Bolívar, and Meta. In 2024, thanks to this partnership, the organizations succeeded in influencing territorial development plans. In 2025, the process moved toward alignment with public policies, a significant step because these policies provide a broader and more binding framework that ensures continuity of the achievements in the development plans, expands the impact of local agendas, and strengthens the capacity of women’s organizations to demand their sustained implementation. Of these 34 women’s civil society organizations, 19 are formal and 15 are informal. Additionally, in coordination with Conexión ICCO, representatives from 33 women’s civil society organizations participated in two sessions in the departments of Nariño and La Guajira, with the aim of strengthening the advocacy and civic oversight capacities of women social leaders to advance the Women, Peace, and Security agenda and the territorial implementation of the National Action Plan for Resolution 1325. Of these 33 women’s civil society organizations, 17 are formal and 16 are informal. Explanatory notes: *We count as women’s civil society organizations those reported by the women on the attendance list. It is important to note that there may be 1, 2, 3, or more women representatives from the same civil society organization. *The results of the IO 4.3 indicators are not cumulative. The women-led civil society organizations (CSOs) involved are part of a multi-phase process in which they will continue to work. | 0 | There is a deviation from the proposed target, resulting from the work carried out in partnership with LIMPAL Colombia, aimed at strengthening the capacities of women’s organizations and their advocacy in the formulation and monitoring of public policies for women in their municipalities. This process was significantly expanded with the aim of ensuring continuity and building on the progress achieved in 2024 regarding advocacy on Territorial Development Plans. Additionally, the partnership established with ICCO expanded the scope of the actions, enabling work with new women’s organizations to consolidate advocacy agendas regarding the National Action Plan for the implementation of United Nations Security Council Resolution 1325.

## GEN
| Leap 4 Peace | Organization: GEN
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2025 (Totals Jan-Sept) | Description | Target 2025 | Explanation deviation
LTO1 | Peace ambassadors collaborate to jointly identify challenges and priorities for women’s meaningful participation in formal peace structures. | # women (aspiring) leaders trained | 15 | 15 women peace builders are trained and mobilized in 2025 through creating spaces for dialogue as well as through organizing networking workshops. | 15
| Network of peace ambassadors are established and functional. | # multi-stakeholder dialogue/platform meetings | 3 | There were 3 multi-stakeholder dialgoue/ platform meetings: 1) coordination workshop in Mae Sot between CSOs, WROs, WPBs, and NUG; 2) Women's Protection Law Consultation Workshop in Mae Hong Song between CSOs, WPBs, and subnational level governance actors; and 3) Advocacy meetings in Jakarta betwen WPBs, WHRDs, and ASEAN staekholders. | 3
| Network of peace ambassadors are established and functional. | # agreements reached as a result of dialogue platform meeting | 1 | There was a draft women protection bill developed and submitted to congress of the subnational level governance institution. | 1
| Network of women peace ambassadors advocate jointly for women nomination and participation in the formal peace process at various levels. | # of advocacy initiatives carried out by political actors | 1 | In advocacy trip in Jakarta, we met with ASEAN Institute for Peace and Reconciliation (AIPR), and as a result of the meeting with them, they advocated back within their institution to extend invite to Myanmar WHRDs to attend Community of Practice (CoP) workshops in ASEAN. | 1
LTO2 | CSOs are willing to collaborate, coordinate and participate in joint lobby and advocacy activities | # of women-led CSOs included in the programme activities | 15 | There were 15 women-led CSOs participating in the project activities during 2025. | 6 | In 2025, there were many of meetings, workshops, and advocacy initiatives that we could organize for women-led organizations. That is why the number of women-led CSOs included in the programme activities are more than we expected before.
| CSOs to collaborate on a joint advocacy agenda on gender sensitive policies, procedures and practices in formal peace structures. | # multi-stakeholder dialogue meetings | 3 | There were 3 multi-stakeholder dialgoue/ platform meetings: 1) coordination workshop in Mae Sot between CSOs, WROs, WPBs, and NUG; 2) Women's Protection Law Consultation Workshop in Mae Hong Song between CSOs, WPBs, and subnational level governance actors; and 3) Advocacy meetings in Jakarta betwen WPBs, WHRDs, and ASEAN staekholders. | 3
| CSOs to lobby with peace process leadership for increased meaningful participation of women in the State and Regional Dialogues | # of regional advocacy initiatives carried out by CSOs | 2 | There were two regional advocacy initiatives carried out by CSOs in 2025. The first one is advocacy trip to Jakarta for meeting with ASEAN stakeholders, and the second is the conduction of a side event in Justice Denied Conference in Melbourne focusing on conflict-related sexual violence in Myanmar. | 2
| CSOs effectively monitor implementation of gender sensitive policies, procedures and practices for increased participation of women and positions by the peace process leadership | # women-led CSOs with increased L&A capacities | 5 | Five women-led CSOs have enhanced their lobbying and advocacy capacities through their involvement in our international advocacy activities, particularly at CSW 69, ASEAN Advocacy in Jakarta. | 3 | We did more of international advocacy activities than we expected before. That's why there were more number of women-led CSOs with increased L&A capacities.
| International L&A to restore democracy and human rights in Myanmar and to revisit national policy and legislation for women’s meaningful participation in the peace process that channels and reinforces international treaties and legislation signed by the Myanmar government (CEDAW, 1325, MSDG) | # of international advocacy initiatives carried out by CSOs | 3 | There were 4 collective advocacy initiatives carried out by CSOs in 2025: CSW 69, ASEAN Advocacy trip to Jakarta, and Justice Denied Conference in Melbourne. | 1 | There were international advocacy opportunites in 2025, more than we expected before.

## NIMD_MMR
| Leap 4 Peace | Organization: NIMD Myanmar
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2025 (Totals Jan-Sept) | Description | Target 2025 | Explanation deviation
LTO1 | Peace ambassadors collaborate to jointly identify challenges and priorities for women’s meaningful participation in emerging democratic peace-making processes | # women (aspiring) leaders trained | 42 | The current 42-member WoPA community from political parties and CSOs in Shan State is continuously enhancingg their skills through monthly networking meetings, working group activities, and mentorship supports. | 42 | The project initially targeted participation from 42 Women Peace Ambassadors (WoPA). Despite challenges caused by conflict-related displacement and limited internet and electricity access in some areas, most WoPA members have continued to actively participate in the monthly networking meetings whenever possible. On average, 35–38 WoPA attended each session.
| Network of peace ambassadors are established and functional. | # multi-stakeholder dialogue/platform meetings | 9 | Organized 6 Networking meetings and 3 Working Group meetings, total 9 online meetings for 42 WoPA community. | 6 | 3 more working group meetings were organized
| Network of peace ambassadors are established and functional. | # agreements reached as a result of dialogue platform meeting | 15 | WoPA members collectively agreed to implement (13 action plans for 2025+ One comprehensive referral system + one reliable service provider list to refer for gender based violence cases, domestic abuses, etc). So total 15 agreements | 2 | 42 WoPAs discussed and agreed on 13 action plans with specific targets to implement their initiatives in their respective areas in 2025, one referral guidelines and one service mapping, total 15 agreements
| Network of women peace ambassadors advocate jointly for women nomination and participation in the formal peace process at various levels. | # of advocacy initiatives carried out by political actors | 151 | A total of 151 WPS-related cases in Myanmar (Shan State) were referred by WoPAs, exceeding the target of 50. Referrals followed established guidelines and covered 14 types of support, including healthcare, psychosocial support, legal assistance, safe shelter, mediation, and access to justice. 15% of cases involved counselling, while 13% related to healthcare and knowledge support. All cases focused on protecting women from violence and supporting recovery in conflict areas and were handled collaboratively by WoPAs. In addition, 9 WoPAs informally engaged 33 leaders from ethnic armed groups, advocating for the WPS agenda and women’s participation in leadership. | 50 | The indicator was originally designed to measure advocacy initiatives by political actors, but was revised in 2025 to track # of cases handled or or referred by WoPAs WoPAs (former politicians, democratic activists) due to conflict, limited civic space, and restricted access to formal advocacy channels. This adaptation ensured a more feasible and context-relevant measure of results, capturing direct support to women affected by violence. The achievement of 151 cases reflects strong progress against the revised target. While not captured under the revised indicator, informal advocacy with 33 ethnic armed group leaders demonstrates continued progress toward the original objective.

## GAPS
| Leap 4 Peace | Organization: GAPS
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2025 (Totals Jan-Sept) | Description | Target 2025 | Explanation deviation
LTO1
LTO2 | International L&A for supportive national policy environments | # of international advocacy initiatives carried out by CSOs | 4 | GAPS and consortium partners carried out four key international advocacy initiatives in 2025: (1) dissemination of the LEAP4Peace Paper Series through global policy forums and WPS Week events; (2) bilateral advocacy with the UK Government and donors on safeguarding WPS funding; (3) participation in the LEAP4Peace end-of-year workshop in Colombia with international representation; and (4) production and promotion of Mind the GAPS podcast | 1 | We ended up doing more activity initaitves than we had already planned.
| International L&A for supportive national policy environments | # studies for evidence-based L&A disseminated to political actors | 4 | Four studies (three country papers Burundi, Colombia, Myanmar and one global paper) were disseminated to political actors, donors and policymakers throughout 2025. The papers were shared via the GAPS website, bilateral meetings, international advocacy events and digital platforms. | 0 | We just used the four studies we had worked on and made sure that they were referenced and dissemnated in out other work on WPS.
| CSOs effectively lobby for policy change and implementation | # of other CSOs with increased L&A capacities | 5 | Approximately five women’s rights organisations (WROs) and civil society partners in Burundi, Colombia and Myanmar demonstrated increased advocacy capacity through participation in the LEAP4Peace end-of-year workshop, joint learning exchanges and use of the LEAP4Peace Paper Series for advocacy. | 0 | These are organisations that were present in Colombia, ,we were fortunate to all meet this year - and we were not expecting to be able to that this final year hence the 0 target.
| CSOs effectively lobby for policy change and implementation | # of other CSOs included in the programme activities | 15 | CSOs participated in LEAP4Peace activities in 2025, including national partners, WROs engaged in the Bogotá workshop, and those featured on Mind the GAPS podcast and dissemination events. This engagement strengthened cross-country networks and visibility of women peacebuilders within the international WPS community | 2 | This is a total number of engagemetn we have had with groups across the year on different activities in realtion to work done on L4P. This was more than expected.

## Example (hidden)
|  | Power of Dialogue | Organisation: XXXX
|  | Planning, Monitoring and Evaluation Framework | Country: XXXXX
Pathway 1 |  | Outcome Indicators |  | Pathway 2 |  | Outcome Indicators
| 1.Consortium partners (NIMD & AMwA) and XXXX are effective enablers of change | # international L&A resolutions on democratic space adopted |  |  | 2. Aspiring and elected young and women are influential actors of change within CSOs targeting youth and women, political party youth leagues, parliament and county assemblies | # of women and youth involved in politics who feel they are able to participate in decision-making processes
|  | Intermediate / output indicators | Types of interventions |  |  | Intermediate / output indicators | Types of interventions
| 1.1 Engage in joint planning, pool resources, coordinate communication messages (joint events), organize joint M&E and learning | # of consortium partners/partners/country office members trained | Organisational capacity building activities |  | 2.1 Strengthen their capacity to organize and mobilize resulting in increased participation and impact in political processes | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | Skills training for young and women leaders (“democracy school”)
# of women/youth leaders trained
| 1.2 Builds each other’s organizational capacity and leverage each other’s networks’ | # of CSOs with increased organizational capacities | Peer learning around use of social media/technology, use of infographics, leveraging reg. And global networks |  | 2.2 Lobby and advocate for youth and women participation in decision making to hold leadership roles in parliamentary and county committees | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) | Sensitize party leaders on youth and women political participation through research-informed advocacy .
# of studies for evidence-based L&A disseminated
| 1.3 Participate in L&A training and develop a joint lobby and advocacy strategy for shared policy goals | # of consortium partners/partners/country office members trained | Training on L&A |  | 2.3 Unite, showcase and amplify diverse young and women voices within parliament and county assemblies | Outcome Harvesting | Use online outreach tools to showcase the work of young and women voices/experiences
This example is adapted from an existing country programme PoD ToC. Please note the contextualized intermediate outcome and outcome statements, also interventions and indicators have been added. For this example just pathways 1 and 2 are worked out.