## Tunisia
|  | Power of Dialogue | Organization: CEMI
Indicator Reporting template
|  | (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description | Target 2023 | Explanation deviation
| Pathway 1 | 1. THE CONSORTIUM, PARTNER NETWORKS AND LOCAL CSOS ARE EFFECTIVE ENABLERS OF CHANGE | Outcome Harvasting
|  | 1.1 The PoD Consortium works complementary | Outcome Harvesting
|  | 1.2 The PoD Consortium builds each other’s, partner networks’ and local CSOs’ capacity | Outcome Harvesting
|  | 1.3 PoD Consortium engages in joint L&A at all levels | # of international L&A campaigns | 0 | No activity realized for the international L&A campaigns | 0 | 0
Pathway 2 (National Level) |  | 2. ASPIRING YOUNG AND WOMEN POLITICAL AND CIVIC LEADERS ARE INFLUENTIAL ACTORS OF CHANGE | # of women and youth involved in politics who feel they are able to participate in decision-making processes | ToT: 12 participants,5 Women, 7 Men (12 Youth). 1st level mixed class TSoP1 :81 participants, 38 women, 43 men (77 Youth). | 74 out of 93 participants from 1st level mixed class TSoP1 and ToT felt that they are able to participate in decision making process. 64 participants from 1st level mixed class TSoP1 (34 Women and 30 Men) and 10 participants from ToT (4 Women and 6 Men). | 93 (Total participants TSoP1+Tot) | the results reported as collected in the survey
|  |  | Outcome Harvesting | On May 2023, 11 out of 20 members of the new elected executive bureau of the political party «Democratic Courant» are TSoP Alumni/participants. On May 2023, Nabil Hajji TSoP Alumni was elected secretary general of the political party «Democratic Courant». In the 2nd of December 2023, some of TSoP Alumni from “Al Machrou3” party and “Al Badil” Party were elected in the executive bureau of the new party “Haq Mouvement” they have created with other youth. | The skills and knowledge acquired during the different TSoP Training cycles helped shaping the participants' profils and capacities to be able to reach high positions within their political party and therefore be effective enablers of change. The skills and knowledge acquired during the different TSoP Training cycles helped affirming his leadership and capacities to be able to reach high positions within the political party and therefore be effective enabler of change. Youth who were in other political parties and who still believe in their role in public affairs and decided to create a new party and named it “Haq movement”. TSoP Alumni were elected in leading roles in the executive bureau of the new party. |  | No deviation
|  | 2.1 Strengthen their movements or organizations | # of CSOs with increased organizational capacities (youth led) | 22 CSOs with increased organizational capacities (Youth Led) out of 23 CSOs. | 22 CSOs out of 23 with increased organizational capacities and leaded by youth. | 14 | No deviation
|  |  | # of CSOs included in the PoD programme (youth led) | 22 CSOs: 11 political parties+ 11 organizations. | 11 political parties and 11 organizations included in the PoD program and leaded by youth. | 14 | No deviation
|  | 2.2 Strengthen their capacities of lobbying and advocacy in decision-making | # of women/youth leaders trained | 1st level mixed class TSoP1: 81 participants, 41 Women and 40 Men. 77 Youth trained out of 81 participants. 48 Youth leaders trained out of 77 youth participants. 21 Women Youth Leaders. ToT: 12 participants, 5 women and 7 Men. All the 12 participants on the ToT cycle are Youth. 10 Youth Leaders: 3 Women and 7 Men. 3 Women Youth leaders on the ToT cycle. | 93 participants participated in the training cycles for 2023 of which 46 Women and 47 Men trained from 1st level mixed class TSoP1 and ToT to strengthen their capacities of lobbying and advocacy in decision-making. 58 youth leaders from both 1st level mixed class TSoP1 and ToT, included 24 women leaders. | 88 | No deviation
|  |  | # of representatives (men/women) of political actors have participated in democratic values oriented training activities (e.g. democracy schools) | 1st level mixed class TSoP1: 81 participants, 41 Women and 40 men. ToT: 12 participants, 5 women and 7 men. | 93 participants participated in the training cycle planned for 2023 of which 46 Women and 47 Men trained from 1st mixed class TSoP1 and ToT. | 88 | No deviation
|  | 2.3 They will be able to amplify diverse young and women voices (dissemination/duplication) | # of women/youth leaders trained | 1st level mixed class TSoP1: 81 participants, 41 Women and 40 Men. 77 Youth trained out of 81 participants. 40 youth women trained out of 41 Women. 48 Youth leaders trained out of 77 youth participants, 21 Women Youth Leaders. ToT: 12 participants, 5 women and 7 Men. All the 12 participants on the ToT cycle are Youth. 10 Youth Leaders: 3 Women and 7 Men. 3 Women Youth leaders on the ToT cycle. Youtube channel "Freesh": 127 videos, 77 posts. Facebook: 70 videos, 28 posts. Youtube: 19 videos. Instagram: 38 videos, 49 posts. | For the ToT and 1st level mixed class TSoP1 , we have 93 participants. 77 youth participants included 40 women from 1st mixed class TSoP1 participated in the cycle planned for 2023. 21 women youth leaders on the 1st level mixed class TSoP1. All the 12 participants on the ToT class are youth. 3 women youth leaders on the ToT cycle. Youtube Channel: 127 videos and 77 posts. | 98 participants 100 videos | No deviation
|  |  | Outcome Harvesting | In April 2023, Rawe Elkefi, TSoP Alumni, performed in a freesh video (one of CEMI’s program) addressing water resources shortage issue reaching an important number of views and shares by activists and local associations. (88 shares and 5.3 K view). In May 2023, following the publication by CEMI of her paper, Rawe elkefi, TSoP alumni, was invited as the sole representative from North Africa to the Fair Water Footprint workshop, organized by Water Witness International in Addis Ababa. | Throughout its different programs, CEMI capacitated the participant with the necessary tools, knowledge and skills in order to be effective enabler of change and provided a digital space (Freesh) where the youth can disseminate their ideas. Throughout its different programs, CEMI capacitated the participant with the necessary tools and knowledge related to drafting policy papers and elaborating public policies. |  | No deviation
Pathway 2 (Regional Level) |  | 2. ASPIRING YOUNG AND WOMEN POLITICAL AND CIVIC LEADERS ARE INFLUENTIAL ACTORS OF CHANGE | # of women and youth involved in politics who feel they are able to participate in decision-making processes | Regional Academy: 20 participants,9 women and 11 men. 19 of 20 participants include 9 women and 10 men, felt that they are able to participate in decision-making process on regional level. Regional Seminar: 28 participants, 12 women and 16 men. 27 of 28 participants include 12 women and 15 men, felt that they are able to participate on dcision-making process on regional level. | 19 of 20 participants include 9 women and 10 men, felt that they are able to participate in decision-making process on regional level. 27 of 28 participants include 12 women and 15 men, felt that they are able to participate on dcision-making process on regional level. |  | no deviation
|  |  | #Outcome Harvesting | In May 2023, the participants of CEMI Regional Academy suggested to create a space for MENA Youth to discuss regional issues. On 2nd of June 2023, the participants of CEMI Regional Academy joined by the TSoP Alumni realized a first round of discussion of their initiative called "Youth Talks". | This highlights CEMI's crucial role as an incubator for youth from MENA Region providing them with a common space for reflexion and collaboration. This highlights CEMI's crucial role as a promotor of open, safe and inclusive spaces anchoring the culture of dialogue and tolerance. |  | No deviation
|  | 2.1 Strengthen their movements or organizations | # of CSOs with increased organizational capacities (youth led) | Regional Academy: 18 CSOs with increased oragnizational capacities: 3 political parties and 15 organizations. | Regional Academy:18 CSOs with increased organizational capacities. | 8 | No deviation
|  |  | # of CSOs included in the PoD programme (youth led) | 38 CSOs included in PoD programme (youth led). Regional Academy:18 CSOs included in the PoD program (youth led): 3 politcial parties and 15 organizations. Regional Seminar: 22 CSOs included in the PoD program (youth led): 13 political parties and 9 organizations. | 18 CSOs were represented in the CEMI Regional Aacademy. 22 CSOs were represented in the CEMI Regional Seminar. 2 of them were represented in the CEMI Regional Academy. | 8 | No deviation
|  |  | Outcome Harvesting |  |  |  | No deviation
|  | 2.2 Strengthen their capacities of lobbying and advocacy in decision-making | # of women/youth leaders trained | Regional Academy: 20 participants, 9 Women and 11 Men. 13 youth leaders trained out of 20 participants. 5 Women leaders trained out of 9. | 20 participants of which 13 youth leaders including 5 women leaders. | 27 | No deviation
|  |  | Outcome Harvesting |  |  |  | No deviation
|  | 2.3 They will be able to amplify diverse young and women voices (dissemination/duplication) | # of women/youth leaders trained | Regional Academy: 20 participants, 9 Women and 11 Men. 13 youth leaders trained out of 20 participants. 5 Women leaders trained out of 9. Regional Seminar:28 participants included 12 experts and 16 youth participants. 12 Women and 16 Men. 8 youth leaders out of 16 youth participants. 5 women leaders out of 12. | 20 participants were part of the CEMI Regional Academy. 13 youth leaders trained out of 20 participants. 5 Women leaders trained out of 9. 28 participants were part of the CEMI Regional Seminar. 8 youth leaders out of 16 youth participants. 5 women leaders out of 12. | 27 | No deviation
|  |  | # of representatives (men/women) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | The CEMI Regional Academy: 20 participants, 9 Women and 11 Men. The CEMI Regional Seminar: 28 participants included 12 experts and 16 youth participants. 12 Women and 16 Men. | 20 youth participants from Jordan, Libya, Algeria and Morocco were present during the Regional Academy. 28 participants included 12 experts and 16 youtn participants from Jordan, Libya,Algeria, Morocco, Irak and Tunisia were present during the Regional Seminar. | 27 | No deviation
|  |  | Outcome Harvesting | In May 2023, the participants of CEMI Regional Academy suggested to create a space for MENA Youth to discuss regional issues. On 2nd of June 2023, the participants of CEMI Regional Academy joined by the TSoP Alumni realized a first round of discussion of their initiative called "Youth Talks". | This highlights CEMI's crucial role as an incubator for youth from MENA Region providing them with a common space for reflexion and collaboration. This highlights CEMI's crucial role as a promotor of open, safe and inclusive spaces anchoring the culture of dialogue and tolerance. |  | No deviation
Pathway 3 |  | 3.POLITICAL AND CIVIC ACTORS COLLABORATE PEACEFULLY ON A BASIS OF TRUST | Outcome Harvesting
|  | 3.1 Build trust to enable alliances | #of interparty dialogue meetings (at national level) | TSoP Debates: 5 Debates. MDP meetings:0 Consultative Council: 1 consultative council. | TSoP Debates: 157 participants, 79 Women and 78 Men. Consultative Council: 8 participants, 1 Women and 7 Men. | 6 TSoP debates 4 MDP meetings 2 consultative council
|  |  | # of representatives (men/women) of political actors have participated in democratic values oriented training activities (e.g. democracy schools) | TSoP Debates: 157 representatives of political and civic actors. MDP meetings:0 Consultative Council: 8 members of consultative council. | 5 TSoP Debates were held with the participation of 157 representatives of political and civic actors, 79 Women and 78 Men. 1 Consultative Council was held with the participation of 8 members, 1 Women and 7 Men. | 440 | No deviation
|  | 3.2 Address grievances through mediation | # of agreements reached (reform agendas / policies / legal amendments) | 0 agreement | no agreement have been reached for this | 1 | The deviation happened due to the current political situation
|  |  | # of civic/political actors trained in dialogue/mediation | Couscous politique: 48 participants. 48 representatives of political and civic actors: 19 Women and 29 Men. TSoP Debates: 157 participants. 157 representatives of political and civic actors: 79 Women and 78 Men. Youth collaborative platform: 93 participants. 93 representatives of political and civic actors:48 Women and 45 Men. | 2 couscous politique includes 48 representatives of political and civic actors. 5 TSoP debates at CEMI office includes 157 representatives of political and civic actors. 3 Youth collaborative platform includes 93 representatives of political and civic actors. A total of 298 representatives of political and civic actors. | 370 participants | no deviation
|  | 3.3 Participate in meaningful dialogue | # of interparty dialogue meetings (at national level) | 2 Couscous politique. 5 debates: 5 TSoP debates. | 7 interparty dialogue meetings were organized: 5 TSoP debates and 2 Couscous politique. | 14 | no deviation
Outcome Harvesting
Pathway 4 |  | 4. POLITICAL AND CIVIC ACTORS STRENGTHEN DEMOCRATIC SPACE | # of workshops related to inclusive policy making | 1st level mixed class TSoP1: 265 workshops. ToT:192 workshops. | 457 workshops are realized during the training sessions of 1st level mixed class TSoP1 and ToT as a part of the inclusive policy-making processes at the national level. | 425 | no deviation
|  | 4.1 Adhere to existing democratic rules | # of representatives (men/women) of political actors have participated in democratic values oriented training activities (e.g. democracy schools) | 12 policy papers. 20 policy briefs. 2 books. 1 Analysis note. 1st level mixed class TSoP1: 81 participants, 41 Women and 40 Men. All the participants are a representatives of political and civic actors. ToT: 12 participants, 5 women and 7 Men. 12 representatives of political and civic actors. Youth Council: 30 participants, 23 Women and 7 Men. 3 Youth Collaborative Platform: 93 participants, 48 Women and 45 Men. All the 93 participants are representatives of political and civic actors. 2 Couscous politique: 48 participants, 19 Women and 29 Men. 48 representatives of political and civic actors. 5 TSoP Deabtes: 157 participants, 79 Woman and 78 Men. 157 representatives of political and civic actors. | 35 publications produced by CEMI's research cell during 2023. 123 participants on the 1st level mixed class TSoP1,ToT and Youth Council programs. The youth collaborative plateform includes 93 participants. The Couscous politique includes 48 participants. The TSoP Debates includes 157 participants. In total, 421 representatives of political and civic actors participated in democratic values oriented training activities. | 409 | No deviation
|  |  | Outcome Harvesting |  |  |  | No deviation
|  | 4.2 Set a space of inclusiveness | # of created/opened spaces for women/youth (at national level) | 5 opened spaces for Women and Youth during 2023. | 5 opened spaces are available for Youth and Women which are the 1st level mixed class TSoP1, Youth Council, Youtube channel (Freesh) Youth Collaborative plateform and Nouabook. | 4 | No deviation
|  |  | # of representatives (men/women) of political actors have participated in democratic values oriented training activities (e.g. democracy schools) | 1st level mixed class TSoP1: 81 participants, 41 Women and 40 Men. ToT: 12 participants, 5 women and 7 Men. Youth Council: 30 participants, 23 Women and 7 Men. Youth Collaborative Platform:93 participants, 48 Women and 45 Men. Youtube channel "Freesh": 199,7K followers Youtube: 42,1K subscribers Facebook: 140K followers Instagram: 17,6K followers | The 1st level mixed class TSoP1 and ToT includes 93 participants. Youth Council: 30 participants. Youth Collaborative Platform:93 participants. A total of 186 participants on the 1st level mixed class TSoP1, ToT and Youth collaborative platform. The Youtube channel "Freesh" still producing videos about different subjects related to tunisian history and to the latest political change. (https://www.youtube.com/@FREESH./videos) | 136 participants 22K followers | No deviation

## Sahel (GORIN)
| Power of Dialogue | Organization: Goree Institute
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Jan-Jun) | Description | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 0 |  | 10 | C'est le nombre de partenaires des différents bureaux du NIM Sahel ayant pris part aux activités de Gorée Institute | 20
| 1.2 PoD Consortium builds capacities | # of CSOs included in the PoD programme (women led) | 13 | C'est le nombre d'organisations dirigées par les femmes ayant participé ce premier semestre aux deux sessions de formation sur (1) le Leadership, espace civique et prévention des conflits : inclusion et participation des femmes et des jeunes et (2) Leadership et prévention des conflits électoraux | 56 | C'est le nombre d'organisations dirigées par les femmes incluses dans le programme et ayant participé aux différentes sessions de formation et de dialogue en 2023. | 15
| 1.2 PoD Consortium builds capacities | # of CSOs included in the PoD programme (youth led) | 29 | C'est le nombre d'organisations dirigées par les jeunes ayant participé ce premier semestre aux deux sessions de formation sur (1) le Leadership, espace civique et prévention des conflits : inclusion et participation des femmes et des jeunes et (2) Leadership et prévention des conflits électoraux | 126 | C'est le nombre d'organisations dirigées par les jeunes inclus dans le programme et ayant participé aux différentes sessions de formation et de dialogue en 2023. | 20
| 1.3 PoD Consortium engages in joint L&A at all levels | # of CSOs with increased organizational capacities (women led) | 13 | C'est le nombre d'organisations dirigées par les femmes ayant participé ce premier semestre aux deux sessions de formation sur (1) le Leadership, espace civique et prévention des conflits : inclusion et participation des femmes et des jeunes et (2) Leadership et prévention des conflits électoraux | 19 | C'est le nombre d'organisations dirigées par les femmes ayant participé aux différentes sessions de formation de 2023 sur le Leadership, espace civique et prévention des conflits, inclusion et participation des femmes et des jeunes, la prévention des conflits électoraux et le programme d'académie de leadership (Mentorship) | 30
| 1.3 PoD Consortium engages in joint L&A at all levels | # of CSOs with increased organizational capacities (youth led) | 29 | C'est le nombre d'organisations dirigées par les jeunes ayant participé ce premier semestre aux deux sessions de formation sur (1) le Leadership, espace civique et prévention des conflits : inclusion et participation des femmes et des jeunes et (2) Leadership et prévention des conflits électoraux | 52 | C'est le nombre d'organisations dirigées par les femmes ayant participé aux différentes sessions de formation de 2023 sur le Leadership, espace civique et prévention des conflits, inclusion et participation des femmes et des jeunes, la prévention des conflits électoraux et le programme d'académie de leadership (Mentorship) | 40
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 67 | C'est le nombre de femmes et jeunes ayant participé ce premier semestre aux deux sessions de formation sur (1) le Leadership, espace civique et prévention des conflits : inclusion et participation des femmes et des jeunes et (2) Leadership et prévention des conflits électoraux | 298 | C'est le nombre de femmes et jeunes dont les capacités ont été renforcées lors des ateliers de formation et les ateliers organisés pas les formateurs accrédités par le Gorée Institute. | 150 | Le Gorée Institute a changé d'approche cette année pour toucher plus de bénéficiaires en accréditant une vingtaine de femmes de jeunes qui doivent former d'autres jeunes de leurs communautés
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 2 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute au cours du 1er semestre 2023 | 8 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute en 2023 | 10
Pathway 3 | 3.1 Political and civic actors address grievances | # of studies for evidence-based L&A disseminated | 0 |  | 3 | C'est le nombre d'études ou de policy briefs publiés pour influencer la participation des femmes et des jeunes | 15
| 3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at regional level) | 2 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute au cours du 1er semestre 2023 | 8 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute en 2023 | 6
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of studies for evidence-based L&A disseminated | 0 |  | 3 | C'est le nombre d'études ou de policy briefs publiés pour influencer la participation des femmes et des jeunes | 2
| 4.2 Civic and political actors safeguard civic space | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at regional level | 2 |  | 3 | C'est le nombre d'études ou de policy briefs publiés pour influencer la participation des femmes et des jeunes | 5
| 4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at regional level) | 2 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute au cours du 1er semestre 2023 | 8 | C'est le nombre de rencontres de formations ou de dialogues organisé par le Gorée Institute en 2023 | 5

## Myanmar
| Power of Dialogue | Organization: NIMD Myanmar
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Jan-Dec) | Description | Targets 2023 | Explain Deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of CSOs included in the PoD programme (other led) | 4 | 4 CSOs included in the POD programme as thematic experts, technical resource person on political knowledge sharing and conducting research for myanmar | 2 | The level of trust from CSO to NIMD is improved throughout the period and gain more participation from them.
| 1.2 PoD Consortium builds capacities | # of civic/political actors trained in dialogue/mediation | 16 | 16 (3 staff members and 13 democractic actors) has been trained in dialogue | 20
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools) | 51 | 51 people (30 male, 20 female, 1 other) political actors representing women, youth and ethnic leaders from Shan, Kayin, Kayah, Mon state have participated in democractic values oriented training activities (i.e. MyDemocracy School training held for 7 days, in person training) | 40 | There are growing numbers of political actors interested to participate in democracy school trainings
| 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 40 | 40 youth and women (20 female, 20 youth) from shan, kayin, kayah, mon state have participated in democractic values oriented training activities (i.e. MyDemocracy School training held for 7 days, in person training) | 40
| 2.1 Y&W leaders strengthen their movements or organizations | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 28 | 1. Political context analysis 2. Needs Assessment 3. Legal and Regulatory Compliance in repressive environments 4. Office Space and Infrastructure 5. IT and Communication Systems 6. Furniture and Office Equipment 7. Staffing and HR management 8. Financial Management 9. Service Agreements with technical experts 10. Communication Plan 11. Secure communication channels 12. Participant vetting and protection 13. Security and Safety Measures 14. Anonymous reporting mechanisms 15. Monitoring and Evaluation Framework 16. Logistics and Supplier Management 17. Alumni Engagement 18. Knowledge Management 19. Democratic Community Sensitization 20. Risk Management 21. Training and Capacity Building 22. Monitoring and Reporting Systems 23. Dialogue facilitation expertise 24. Digital Security Mentoring and Coaching 25. Psychosocial support 26. Documentation and Evidence Gathering 27. Strategic Messaging 28. Continuous Risk Assessment | 20 | Due to the high sensitive political context, more and throough preparation are needed.
Pathway 3 | 3.1 Democratic political actors engage in emerging dialogue at the sub-national level (Shan, Kayin) | # representatives of civic/political actors trained in dialogue/mediation | 15 | 15 people (8 male, 7 female) democratic political actors representing political party, CSOs and ethnic leaders from Kayin State have participated in integrated continuous dialogue meetings. | 30 | Despite 20 confirmed participants, some couldn't attend last minute due to unforeseen circumstances such as conflict escalation, safety concerns, medical emergencies, and personal family issues. New dialogue members from Kayin State will be invited in 2024. Only Kayin State could be targeted for implementation due to the political complexities in Shan State. | Firstly, met bilitary with Shan political party & CSO to creat dialogue platform at Shan State. Due to current high politically, ethnically and geographically diverse in Shan State, it was not the right time to have inclusive political dialogue. So, We change target area from Shan to Mon because Mon state is less conflict than other regions and states. CSOs and political parties are engaging each other and preparing Mon state constitution. It is a positive entry for NIMD to host and support dialogue. In the future, there might be political discussion related to territory between Mon and Kayin. 1.2 Reflect specif
|  | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 28 | 1. Political context analysis 2. Needs Assessment 3. Legal and Regulatory Compliance in repressive environments 4. Office Space and Infrastructure 5. IT and Communication Systems 6. Furniture and Office Equipment 7. Staffing and HR management 8. Financial Management 9. Service Agreements with technical experts 10. Communication Plan 11. Secure communication channels 12. Participant vetting and protection 13. Security and Safety Measures 14. Anonymous reporting mechanisms 15. Monitoring and Evaluation Framework 16. Logistics and Supplier Management 17. Alumni Engagement 18. Knowledge Management 19. Democratic Community Sensitization 20. Risk Management 21. Training and Capacity Building 22. Monitoring and Reporting Systems 23. Dialogue facilitation expertise 24. Digital Security Mentoring and Coaching 25. Psychosocial support 26. Documentation and Evidence Gathering 27. Strategic Messaging 28. Continuous Risk Assessment | 20 | More preparation were needed due to high political sensitivity.
| 3.2 Democratic political actors have built trust across political divides. | # of multi-stakeholder dialogue meetings (at sub-national level) | 11 | Hosted 9 online and 2 in-person dialogue meetings with 15 democratic political actors from Kayin State. | 2 | Due to the need of political situation and high interest of dialogue members to engage each other, number of multi-stakeholder dialogue meetings increased.
|  | # of agreements reached (reform agendas / policies / legal amendments) | 14 | 14 agreements were reached (eg.vision&mision of dialogue, criteria of new dialogue member, strategy, communication, key stakeholders lists, to study relevant constitution of KNU,2008, Mon,Kayah,NUCC/NGU Charter) | 0
| 3.3 Democratic political actors understand the need for dialogue, root causes and consequences of exclusion and conflict. | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 15 | 15 people (8 male, 7 female), a training component was integrated into the concept of dialogue in 2nd dialogue, 4th in Bangkok month of June and the 10th dialogue meeting in Hua Hin, Oct 23-25. | 30 | Originally intended for two states, the plan was adjusted due to an escalation of conflict in the country. As a result, the dialogue is now initiated solely in Kayin State, with the participation of 15 members in 2023.

## Jordan
| Power of Dialogue | Organization: NIMD Jordan
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of multi-stakeholder dialogue meetings (at international level) | 4 | The Network meeting and 3 CDs Council meetings. | 4
| 1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 2 | Staff member completed a training course. Country director attended leadership training. | 4 | Two planned courses were planned but didn't happen due to staff engagement in fundraising.
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 80 | 50 in the SoP and 30 in the PPs leadership programme. All youth below the age of 38 41 women and 39 men | 40 | SoP applicants for 2023 were very good, so we increased the number of students. As for the PPs training, a lot of PPs decided to participate, which was not expected.
| 2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme | 4 | One provided the L&A training, and 3 conducted the local level dialogue sessions. | 5 | One additional CSO was supposed to take part in the dialogue sessions, but they couldn't manage to organize it.
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # Of agreements reached (reform agendas / policies / legal amendments) | 6 | Six agreed policy papers were produced. | 10 | Ten policy papers were planned, but due to the drop-out in the SoP, not all were developed.
| 2.3 Y&W leaders Amplify diverse young and women voices | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 8 | Eight lobby sessions on the local level. | 8
Pathway 3 | 3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at national level) | 3 | Three dialogue sessions on the national level. One dialogue session on the topic of Cybercrimes Law and its effect on political activists with the minister of MoPPA; the participants were from the PPs leadership programme. The other two were on aspects of political youth-led initiatives; the participants were from the SoP alumni | 3 | More dialogue sessions were implemented on the local level.
Pathway 4 | 4.2 Civic and political actors safeguard civic space | # of studies for evidence-based L&A disseminated | 7 | Roadmap to women political participation. Policy papers. | 7 | The budget for the planned two researches was merged in order to conduct the Roadmap, which costs more.
| 4.4 Civic and political actors set shared policy agendas | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 4 | The Launching/positioning event. Dialogue meeting with the minister of MoPPA on the Cybercrimes law, and two alumni meetings. | 4

## Mozambique
| Power of Dialogue | Organization: IMD Mozambique
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 2 | During the year, two intervention were held for this indicator, namely two exchanges of experience between IMD and Nimd-Hethopia involving the alumni from schools to ethiopia democracy and young people of the IMD Youth Democratic Academy. The second intervention was the exchange of experiences between women and young leaders in the politics and civil society of Mocambique and South Africa. | 6 | The difference of 4 was expected to correspond to the formations of institutional employees.
| 1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 8 | During the year, the program contributed to the strengthening of Civic Society's 7 organizations led by women, namely Manas, forum of Community Radios (Forcom), Association for Parliamentary Democracy (ADEPA), Association of Women of Social Communication ( AMCS), Religious Woman Association, Women's Association for Development (Amurede) and Gender Links. And an organization led by a young Male. | 6
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 6 | 3 formal sessions involving political parties and civil society were held and 3 informal sessions. Sessions aimed to influence the electoral manifestos to be elaborated in observance of the perspective of gender and sensitive to youth. | 3 | No deviation from the planned goals were registered.
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 160 | In the first half of 2023 50 women were formed and in the second half were formed 110, in which 35 were from the MDM party, 26 of Renamo and 48 from Frelimo, totaling 160 for the year. | 200 | During planning and being a period of elections, it was expected that the number of graduates would respond or overcome to the planned but the party reduced the number of women formed because they were involved in electoral activities of mobilization.
Pathway 3 | 3.1 Political and civic actors address grievances | # of political/civic actors taken measures enhancing representation of women and youth | 8 | Of the 13 foreseen, only 13 political parties developed hosts to reinforce the representativeness of women in policy and elected institutions, namely MDM, Renamo and Frelimo - these to the level of stopping and new democracy, PAHUMO, asthmatics, AMUSI and Democratic Revolution. | 13 | The deviation derived from the fact that not all 22 political parties, citizen groups and competing coalitions included women such as listed heads for the 2023 autarchic elections. In fact, number 8 is only regarding parties that proposed women to leaders to the CAA -candidacy lists, although all 22 parties have proposed women in the total composition of the application lists.
| 3.1 Political and civic actors address grievances | # of agreements reached (reform agendas / policies / legal amendments) | 1 | The female leagues of the 3 parties with parliamentary representation and civil society agreed to sign 3 instruments, namely: a) A memorandum of understanding between each and IMD. B) a memorandum that unites the 3 alloys for the rheation of joint accents of widening of the political space of women in parties and in the representative bodies and, c) an agreement for the implementation of the Mocambique Women's Political Agenda. These measures were ratified during the exchange of experiences between civil society and political parties of Mocambique and South Africa | 3 | At least 3 agreements or laws of laws would be expected, but the context did not allow the conclusion of the process and this is expected to happen in 2024.
| 3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (women led) | 7 | 7 Organizations of the Civic Society led by women, namely Manas, Forum of Community Radios (Forcom), Association for Parliamentary Democracy (ADEPA), Association of Women of Social Communication (AMCs), Religious Women Association, Women's Association for Development (Amurede) and Gender Links. | 4
| 3.2 Political and civic actors build trust | # of interparty dialogue meetings (at national level) | 3 | During 2023, 3 inter-party dialogue sessions were held in which political parties with and without parliamentary representation participated. These meetings were held as follows: 1. The first meeting was held in South Africa in which Mozambican and South African parliamentary political parties discussed legal and institutional mechanisms for promoting the inclusion of women in politics and governance. 2. Political parties with and without parliamentary representation were influenced by civil society to adopt zebra candidacy lists, as an instrument for greater inclusion of women in parties and elected bodies. 3. Dialogue sessions between party leagues and leaders and between party members and civil society to influence the adoption of the Zebra candidate list. | 3 | No deviation from the planned goals were registered.
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 8 | In 2023 the program conducted 2 advcacia sessions to influence the greater inclusion of women in national political processes. These sessions had the presence of diplomatic entities namely, Netherlands Ambassadors, Suecia, Canada, UK, Finland, General Secretariats of Political Parties, Women's Leagues and Presidents Women of Provincial Assemblies. In parallel to these formal sessions, 6 sessions (two by parties) were performed with the elites or influential people of parties with parliamentary representation, for advocacy to include more women and young people in the summit places of the electoral lists of political parties for the municipality 2023 . | 3 | The fact that informal sessions were performed with political actors, it contributed to the growth of the number of achievements in the year, since in the forecast of Target had not been including the number of informal sessions.
| 4.2 Civic and political actors safeguard civic space | # of multi-stakeholder dialogue meetings (at national level) | 1 | In 2023 a dialogue was held that gathered organizations that work in the social and political engagement of women and the deputies of the Assembly of the Republic of Renamo, Frelimo and MDM. The initiative aimed to contribute to more approximation between civil society and elected politicians, contributing to a living that allows the sharing of ideas to improve governance and particular inclusion. | 1 | No deviation from the planned goals were registered.
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wouldn't that count as 3 agreements? Reply: Actually the agreements wasn't signed that's why we can't consider them as already exists.

## Iraq
| Power of Dialogue | Organization: WEO Iraq
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office staff trained | 6 | Training of trainers | 5
| 1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 1 | WOE | 1
| 1.2 PoD Consortium builds capacities | # of CSOs included in the PoD programme (other) | 3 | WOE, CEMI, NIMD | 3
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 24 | 24 Democracy school graduates | 25

## Guatemala
|  | Power of Dialogue | Organization: NIMD Guatemala Regional Programme
Indicator Reporting template
|  | (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 |  | 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 38 | Número de socios/miembros según consorcio que fueron capacitados por la oficina de NIMD GT en los Talleres de Gestión por resultados (38): Taller Team Building: 18 socios/miembros Tejiendo Juntas: 25 socios/miembros Locación; fechas; nombre del taller -Ciudad de Guatemala; 27 y 28 de abril; Análisis político y comunicación estratégica -San Lucas Tolimán; 14 y 16 de julio; Planificación Estratégica -Antigua Guatemala; 25 y 27 de agosto; Diseño de proyectos -Tecpán; 6 de noviembre; Orientaciones para el gasto y ejecución de presupuestos | 10 | El incremento en el número de socios/miembros que fueron fortalecidos en sus capacidades de gestión, se logró establecer debido a la participación del consorcio de denominado "Tejiendo juntas" que se integra por 6 organizaciones de mujeres indígenas, de las cuales, 25 de sus miembros se registraron como participantes de las capacitaciones.
|  | 1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 6 | Número y nombre de las Organizaciones de Sociedad Civil con mayores capacidades organizativas (6): ALIANMISAR, AMUTED, CHOMIJA, CPANESA, IXQ'ANIIL y KOMONMAYAB. 1) Alianza Nacional de Mujeres Indígenas por la Salud, Investigación, Formación e Incidencia Política (ALIANMISAR) 2) Asociación Mujer Tejedora del Desarrollo (AMUTED) 3) Asociación de Abogadas Indígenas Chomijá (CHOMIJA) 4) Centro de Procesamiento de Alimentos Nueva Esperanza (CPANESA) 5) Asociación de Mujeres Ixq'aniil Palaq Ha' (IXQ'ANIIL) 6) Komon Mayab' (KOMONMAYAB) | 3
Pathway 3 |  | 3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (women led) | 6 | Número de Organizaciones de Sociedad Civil incluidas en el programa PoD -liderado por mujeres- (6): ALIANMISAR, AMUTED, CHOMIJA, CPANESA, IXQ'ANIIL y KOMONMAYAB. | 6
|  | 3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (other led) | 31 | Número de Organizaciones de Sociedad Civil incluidas en el programa PoD -otros liderazgos- (31): 6 OSC conforman el consorcio Tejiendo Juntas en Guatemala 25 OSC conforman el consorcio EcoFeminismos en El Salvador | 30
|  | 3.2 Political and civic actors build trust | # of interparty dialogue meetings (at national level) | 1 | Número de reuniones de diálogo interpartidista -a nivel nacional- (1): Boot Camp El Salvador DIálogo Multiparidario con los partidos políticos: VIVA, MOVIMIENTO SEMILLA, CABAL y COMPROMISO, RENOVACIÓN Y ORDEN (CREO) Resultado: Inciativa de conformar una mesa multipartidaria de “Jóvenes por la democracia” | 5 | El 2023 fue un año de contexto político electoral difícil en cuanto a la garantía sobre la conservación de la certeza jurídica, que de flaquear, amenazaba la prevalencia de ciertos partidos políticos, entre ellos el del actual presidenciable proveniente de la postulación con el partido político movimiento semilla. Esto ocasionó un contexto de descontento popular, extensas manifestaciones y que el trabajo para desarrollar diálogos multipartidarios (con los partidos políticos validados por el Tribunal Supremo Electoral) fuera complejo de organizar.
|  | 3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at national level) | 17 | Número de reuniones de diálogo multilateral -a nivel nacional- (17): 17 diálogos electorales dieron como resultado 17 agendas ciduadanas | 5 | El proceso electoral del 2023 permitió que se facilitaran a nivel nacional (entre las OSC) los diálogos electroales dirigidos por grupos promotores. El resultado de estos, fue la composición de 17 agendas ciudadanas para la incidencia.
|  | 3.4 Political and civic actors attend to root causes | # of women/youth leaders trained | 246 | Número de mujeres y líderes juveniles capacitados (213): Tejiendo Juntas: 25 mujeres y líderes juveniles capacitados Locación; fecha; capacitación: Ciudad de Guatemala: 27 y 28 de abril. Análisis político y comunicación estratégica San Lucas Tolimán: 14 y 16 de julio. Planificación Estrategica Antigua Guatemala: 25 y 27 de agosto. Diseño de proyectos Tecpán: 6 de noviembre. Orientaciones para el gasto y ejecución de presupuestos Caminemos: 188 mujeres y líderes juveniles capacitados (125 mujeres y 63 jóvenes) Capacitación; Locación; Fecha: Talleres de negociación y diálogo político para evitar conflictividad en proceso electoral 2023 Sesión 1: Curso con delegados del TSE - Jutiapa 15 de marzo del 2023 Sesión 2: Curso con Juntas Electorales - Jutiapa 16 de marzo del 2023 Sesión 3: Curso con delegados del TSE - Escuintla 13 de abril del 2023 Sesión 4: Curso con Juntas Electorales - Escuintla 14 de abril del 2023 Sesión 5: Curso con delegados del TSE - Zacapa 20 de abril del 2023 Sesión 6: Curso con Juntas Electorales - Zacapa 21 de abril del 2023 Sesión 7: Curso con delegados del TSE - Quetzaltenango 10 de mayo del 2023 Sesión 8: Curso con Juntas Electorales - Quetzaltenango 11 de mayo del 2023 Sesión 9: Curso con delegados del TSE – Antigua GUA. 18 de mayo del 2023 Sesión 10: Curso con Juntas Electorales - Izabal 20 de mayo del 2023 Sesión 11: Virtual, invitación a todas y todos 5 de junio del 2023 El Salvador. Formación protección para defensores de Derechos Humanos (33 personas) | 50 | El contexto electoral permitió el fortalecimiento de capacidades de juntas electorales departamentales a nivel nacional.
| Pathway 4 | 4.4 Civic and political actors set shared policy agendas | # of studies for evidence-based L&A disseminated | 1 | Número de estudios difundidos sobre L&A basados en evidencia (1): Actualización del documento de análisis "Techo de Cristal y Agenda política para la mujer Política", trabajado desde octubre 2023 y publicado en febrero 2024 | 1

## Mali
| Power of Dialogue | Organization: NIMD Mali
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description | Target 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0 | Il s'agit de plaidoyer mener au niveau régional par les partenaires du PoD. | 1 | Le Consortium PoD, en particulier la collaboration entre l'Institut Gorée et le NIMD Sahel n'a pas encoure abouti à un plaidoyer regional même les réflexions et les échanges ont beaucoup avancé dans ce sens.
| 1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 3 | Comme planifié, les 03 bureaux du NIMD Sahel ont approfondi les analyses d'économie pays sur la question spécifique de la particpation électorale des femmes dans le Sahel | 3
| 1.3 PoD Consortium engages in joint L&A at all levels | # of regional L&A campaigns | 1 | Il s'agit des actions communes entre partenaires du PoD, ici il l'action concerne l'action du NIMD sahel sur la question de la participation électorale des femmes dans le Sahel. | 1 | L'atelier de capitalisation au Niger a été l'occaision de faire un plaidoyer régional auprès des élues nigérences et des représentantes de l'administration du Niger. Ensuite, L'appel de Niamey a été partagé avec les autorités nationales des trois pays.
| 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 16 | La collaboration entre les partenaires PoD à travers le partage d'expériences et d'outils. | 10 | Le staff des 03 bureaux du NIMD Sahel a été renforcé sur le feminisme par le partenaire AKINA Mama Wa Afrika. 16 membres du staff NIMD Sahel au lieu des 10 initialement prévus ont bénéficié de la session de formation en ligne.
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 375 | Les organisations partenaires de jeunes et de femmes qui bénéficient des sessions de renforcement de capacité sur des questions spécifiques. | 90 | Le NIMD a renforcé les connaissances de 36 jeunes dont 15 femmes en Lobbying et Plaidoyer. Le partenaire OCGS a formé exclusivement 240 jeunes femmes sur les Réformes constitutionnelles et les élections au Mali. Ces formations ont lieu à Bamako, Sikasso, Segou, Mopti. L'association Vision Femmes Mali a renforcé les connaissances et compétences de 99 femmes de la commune 1 de Bamako sur les questions de démocratie et de gouvernance locale.
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 2 | Des activités de L/P des jeunes et des femmes pour améliorer leur accès aux postes électifs et nominatifs. | 1 | Le Consortium des organisations civiques et politiques de jeunes et de femmes ont organisé une journée d'échanges avec le ministère délégué aux réformes dans le cadre du plaidoyer autour de leurs recommandations qu'ils portent sur la Charte des partis politiques. Les états génraux de la jeunesse ont constitué également un espace de plaidoyer pour le consortium afin d'interpeller les autorités nationales sur la place des jeunes dans les prises de décisions. Il est à noter que le Consortium a un document de plaidoyer validé par les organisations membres et dont le partage se poursuivra avec les autorités nationales et les partenaires internationaux.
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 1 | Les espaces physiques et virtuels au niveau régional pour amplifier les voix des jeunes et renforcer leur participation à la vie politique. | 0 | Les alumni des écoles politiques et démocratiques ont mis en place un espace virtuel d'échanges sur les problématiques régionales, appelé Masterclasse Sahel.
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 2 | Les espaces physiques et virtuels au niveau national pour amplifier les voix des jeunes et renforcer leur participation à la vie politique. | 1 | Ces espaces crées et ouverts sont Espace DJEMU animés par des alumni de la promotion Thomas Sankara et Mussow Ka Faso Jo Baroni mis en œuvre par l'association Vision Femmes Mali
Pathway 3 | 3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 4 | L'engagement des acteurs publics à améliorer la place des jeunes et des femmes dans la gouvernance. | 2 | Alioune Gueye (membre du Conseil National de Transition), Moussa Mara (ancien Premier ministre et candidat investi du Parti YELEMA), le ministre de la jeunesse et des Sports, et le Président de la Transition, le chef de l'Etat se sont engagés publics à donner plus de place aux jeunes et femmes.
| 3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at national level) | 16 | Il s’agira des cadres de d'échanges multi-acteurs de nos partenaires, des espaces de réflexion entre citoyens et acteurs politiques autour des enjeux de réformes dans la perspective de la refondation. | 9 | L'OCGS a organisé des Assemblées populaires sur "L'implication des autorités traditionnelles et religieuses dans la gouvernance au titre de la IVe république au Mali : défis et perspectives " à Ségou, Sikasso, Mopti, Gao, et avec les 06 communes de Bamako. L'Association Démocratie 101, dans le cadre de la semaine de célébration des journées de la paix, de la démocratie et de la reconsiliation nationale, a organisé 04 grins citoyens et 02 théâtres forums sur les idées reçues de la démocratie malienne. Le CPSRE a initié un Forum d'échanges interpartis comme cadre de réflexion des partis politiques.
| 3.4 Political and civic actors attend to root causes | # of studies for evidence-based L&A disseminated | 1 | Il s'agit des études menées réalisées pour alimenter le débat public sur des questions spécifiques. | 3 | Le bureau du Mali a fait une étude sur La visibilité médiatique des femmes pendant les élections. Le partenaire OCGS qui fait d'ahibute des notes d'analyse, a mis l'accent sur la mise en place des cadre de concertation citoyenne, ce qui n'a pas permis d'élaborer des notes d'analyse ou autres études.
| 3.4 Political and civic actors attend to root causes | # of CSOs included in the PoD programme (other led) | 12 | sept (07) organisations au minimum qui interviendront directement et indirectement aux activités mises en œuvre sous PoD. Ces organisations de la société civile et de regroupements des jeunes et des femmes politiques élargiront la portée de nos interventions aux autres citoyens afin de les informer et les impliquer sur les questions de gouvernance. | 7 | RJPPM, REJEFPO, RFCOPA, D 101, ABM, GRADI Mali, Vision Femmes Mali, CPSRE, COFOR, OCGS, AEEM, Clinique Juridique de ISPRIC sont des organisations de la société civile impliquées dans les activités du PoD. De nouvelles organisations ont sollicité et ont pu bénéficié de l'appui du NIMD.
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 |  | 0

## Niger
| Power of Dialogue | Organization: NIMD Niger
Annexe 2 Indicator Reporting
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0 | La mise en commun des réseaux pour une synergie | 1 | Nous n'avons rien entrepris dans ce sens,
| 1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 3 | Etudes sur la participation de la femme en politique dans chacun des 3 pays Sahel | 3 | Chaque pays dispose d'une note sur le sujet,
| 1.3 PoD Consortium engages in joint L&A at all levels | # of regional L&A campaigns | 0 | Campagne de plaidoyer à l'endroit d'institutions régionales (CEDEAO, UA) | 1 | Malgré les échanges avec l'Institut de Gorée, nous n'avons pas pu nous accorder sur la marche à suivre
| 1.4 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 0 | Formation des staffs des bureaux NIMD Sahel | 10 | La formation avec Akina n'a pas eu lieu.
| 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 17 | Formation des staffs des bureaux NIMD Sahel | 10 | Par contre tout le personnel a été formé sur le team building, les 3 CD ont suivi une formation en leadership, 5 chargés de programme sur le suivi et évaluation des 3 pays et 6 du staff financier en gestion financière . Au Niger le staff a eu renforcement des capacités en anglais
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 174 | Session de formation EPD | 76 | Nous avons pu tenir plus de sessions que prévu suite à l'actualisation de notre programme après le coup d'Etat
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | Les campagnes de plaidoyer | 2 | Suite au coup d'Etat, nous avons du suspendre certaines activités
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 11 | Espaces de dialogue | 2 | 6 tables rondes, 3 cafés politique, 2 conférences publiques et un forum national des jeunes démocrates ont été organisés au profit de plus de 500 personnes,
Pathway 3 | 3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 30 | Plaidoyer pour insertion des jeunes | 200 | Faute de consensus entre organisation des jeunes sur la loi sur le quota,le plaidoyer initialement prévu a été abandonné. Cependant un groupe de 30 jeunes alumnis militants de partis politiques se sont mis ensemble de préparer un plaidoyer conjoint à l'endroit de leurs formations politiques en vue d'une meilleure représentativité.
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 | Campagne de plaidoyer à l'endroit de la CEDEAO | 1 | Aucune campagne n' a pu être menée faute de support,

## Burkina Faso
| Power of Dialogue | Organization: NIMD Burkina Faso
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Jan-Jun) | Description | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0 | Cette activité vise à ouvrir des échanges entre les membres du consortium en vue d'harmoniser les stratégies d’intervention et aussi pour préparer le forum régional NIMD-GORIN. Ce qui aboutira à une campagne de plaidoyer auprès de la CEDEAO | 0 | La campagne de plaidoyer et de lobbying ne s'est pas encore tenue. Toutefois, au sein du consortium, un document visant à déboucher sur un document de plaidoyer et de lobbying a été élaboré et permettra de poursuivre les discussions, | 1 | Les différents échanges entre les membres du consortium n’ont pas encore abouti à un résultat concret.
| 1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 13 | Il s'est agi de former les acteurs du NIMD formés sur des thématiques spécifiques notamment l’approche genre sensible et aussi le renforcement des capacités des partenaires locaux du NIMD sur le dialogue | 14 | Treize (13) membres de l’équipe du NIMD Sahel ont reçu une formation sur le team building. En outre, un partenaire a pu être formé sur la conduite du dialogue multi-acteurs. Au total, 14 acteurs ont bénéficié d'une formation. | 10 | L'écart s'expliuqe par le fait que le NIMD est allé au-delà de la cible fixée
| 1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 2 | Il s'agit d'actualiser le PEA pour l'année 2023, de faire une étude sur la participation politique des femmes au Burkina Faso et de produire un rapport d'étude sur la participation politique des jeunes au Burkina Faso | 3 | Le PEA 2023 du Burkina Faso a été élaboré. Un rapport d'étude sur la particpation politique des femmes a été produit et un rapport sur la participation politique des jeunes est également produit. | 3 | RAS
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 30 | Cette activité vise à renforcer les capacités des femmes et des jeunes en vue de faire d'eux des acteurs de changement | 51 | Trente (30) femmes potentielles candidates aux prochaines élections ont reçu une formation sur le « leadership féminin et le marketing politique » en vue de renforcer leur leadership et leurs capacités en mobilisation de ressources afin de favoriser leur participation effective à la vie politique. | 70 | La cohorte de 40 jeunes alumni à former au titre des écoles politique et démocratique n'a pu être réalisée puisque le NIMD entendait le faire avec le financement de l'UE. Seulement 21 jeunes ont bénéficié d'une formation
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 1 | Il s'agit d'une activité de plaidoyer sous la conduite de la CBDF auprès d'acteurs politiques nationaux dans le but d’un meilleur positionnement des femmes dans les instances de prise de décisions | 1 | Un plaidoyer a été fait à l’endroit de Monsieur le Président de la Délégation Spéciale de la commune de Koudougou relatif à l’accroissement de la participation des femmes et des filles dans les instances de prise de décisions afin de leur permettre de contribuer davantage à la promotion de paix, de la cohésion sociale et de la sécurité | 1 | RAS
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 0 | Il s'agit de créer des espaces virtuels visant l'amplification des voix des jeunes et des femmes au niveau régional | 1 | Sur les quatre (04) cafés politiques régionaux organisés par le NIMD Sahel, le quatrième a permis aux alumnis des trois pays de lancer un appel à la jeunesse de l’Alliance des Etats du Sahel (AES) afin d'approfondir les réflexions vers des actions communes. Le processus est en cours | 1 | RAS
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 1 | Il s'agit de créer des espaces virtuels visant l'amplification des voix des jeunes et des femmes au niveau national | 2 | Deux (02) espaces ont été créés au cours de l'année 2023. La CBDF a réuni les femmes potentielles candidates formées autour d'une plateforme. En outre, les alumni formés ont pu également mettre en place une plateforme | 2 | RAS
Pathway 3 | 3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 0 | il s'agit pour cette activités de mesures ou d'engagements pris par un ou des acteurs politiques ou de la société civile en relation avec le programme du NIMD en vue d'une meilleure représentativité des jeunes et des femmes dans l’espace public. | 1 | Lors de la commémoration de la journée internationale de la démocratie le 15 septembre, le NIMD a tenu un dialogue entre les alumni et une personnalité politique en la personne de Daouda Diallo, 4ème vice-préseident de l'ALT. Ce dernier s'est engagé à accompagner les jeunes alumni pour plus d'engagement et de responsabilité politique | 3 | Sur les acteurs attendus pour l'accompagnement dans l'engagement des jeunes et des femmes, seul un acteur s'est montré volontaire. Cela s'explique par la fragilité et la volatilité du contexte sociopolitique du Burkina Faso avec la restriction des libertés politiques (les activités des partis politiques sont suspendues et certaines OSC sont inquiétées à cause de leurs actions. Du coup, les différents préferent la prudence et refusent de s'exposer publiquement.
| 3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at national level) | 1 | il s'agit ici d'activités de dialogue multi acteurs réalisés | 11 | Le partenaire Balai citoyen a organisé 03 dialogues politiques à Bama. ARGA a tenu 03 cafés politiques et 03 conférences publiques ayant réuni divers acteurs. Enfin, un dialogue s'est tenu entre le 4ème vice-président de l'ALT et les alumni. Un dialogue également a été organisé dans le cadre du forum Africapacités | 8 | Pour 08 dialogues programmés, il a été organisé 11 dialogues. Cela traduit le fait que les échanges avec ARGA ont sucité d'autres cadres de dialogues comme les conférences publiques
| 3.4 Political and civic actors attend to root causes | # of studies for evidence-based L&A disseminated | 2 | Il s'agit ici de diffuser les documents élaborés | 3 | Le PEA 2023 et l'étude sur la participation politique des femmes ont été diffusés | 1 | Une seule étude était prévue pour etre diffusée, mais en définitive, deux études ont éte diffusées
| 3.4 Political and civic actors attend to root causes | # of CSOs included in the PoD programme (other led) | 3 | Il s'agit ici des partenaires de la sociéte civile qui sont inclus dans la mise en œuvre du PoD. | 3 | Trois partenaires de la société civile ont été impliqués dans la mise en oeuvre du PoD. IL s'agit de ARGA pour la réalisation des cafés politiques, de la CBDF qui met en œuvre les activités d'amplification des voix de la femme et Balai Citoyen qui a en charge l'implémentation du volet dialogue. | 2 | Au lieu de 2 partenaires, 03 partenaires ont été impliqués
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 | Il s'agit de campagne de lobbying et de plaidoyer auprès d'acteurs régionaux comme la CEDEAO | 0 | Aucune campagne de Lobbying et de Plaidoyer n'a été faite | 1 | La campagne de plaidoyer et de lobbying ne s'est pas encore tenue. Toutefois, au sein du consortium, un document visant à déboucher sur un document de plaidoyer et de lobbying a été élaboré et permettra de poursuivre les discussions,
Note on J10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Qu'est-ce qui a rendu possible la creation de plus d'espaces que prevu?

## Colombia
| Power of Dialogue | Organization: NIMD Colombia
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 Consolidate their own approach/model to foster collaboration between political and civic actors on lessons of the implementation of innovative multiactor dialogue scenarios | # of studies for evidence-based L&A disseminated | 2 | Se publicaron dos (2) productos relacionados con la participación juvenil, el primero en el marco del Mini Public desarrollado con el proyecto Quórum, se publicó el libro JUVENTUD EN DIÁLOGO: Herramientas para la transformación del sistema político y electoral colombiano, donde el equipo de PoD participó en el capítulo 2 sobre la participación de los y las jóvenes en la reforma política. Y el segundo, corresponde a la participación del caso de estudio sobre Colombia en la publicación del consorcio de PoD sobre Participación Política de la Juventud (YPP) que será publicado en 2024. | 1 | Se reportan dos publicaciones ya que el año pasado no se cumplió este indicador pues la publicación objetivo estaba programada para el 2023
Pathway 1 | 1.3 Enhance their capacities to support collaboration between political and civic actors based on innovation | # of consortium partners/partners/country office members trained | 0 | No se avanzó en este indicador debido a que se había cumplido la meta en 2022, sin embargo en 2024 esperamos generar nuevos espacios. | 15 | Los indicadores para este objetivo han sido cumplidos. Sin embargo, después del intercambio de experiencias en diálogo y facilitación del que participará el equipo en marzo de 2024, esperamos replicar este ejercicio con espacios de formación en facilitación para el staff de NIMD y para las organizaciones socias de la Alianza que puedan sumarse.
Pathway 2 | 2.1 Young strengthen their organizations with increased abilities to partake in political and social processes | # of women/youth leaders trained | 778 | 1. Se formaron 226 jóvenes (hombres) y 169 mujeres (168 menores de 28 y 1 mayor de 28 años) en la fase de formación de Mini Public, para un total de 395. 2. Se formaron en total 217 jóvenes y mujeres, en las 3 versiones de la Escuela de Formación para la Democracia, dirigida a liderazgos, precandidatos y candidatos a las próximas elecciones locales, así como para las Escuelas de Candidatas a Electas realizadas por L4P en alianza con ICCO, donde PoD apoyó con staff y metodologías. *Escuela de candidatas a Electas (CAE) - Nariño: 52 mujeres (11 jóvenes y 39 mayores de 28) *Escuela de candidatas a Electas (CAE) La Guajira: 48 mujeres (6 jóvenes y 27 mayores de 28) *Escuela de Formación para la Democracia (EFD) Bogotá: 47 mujeres (12 jóvenes y 32 mayores de 28) *Escuela de Formación para la Democracia (EFD) Popayán: 7 mujeres jóvenes, 19 mujeres mayores de 28 y 6 hombres jóvenes, total 32 *Escuela de Formación para la Democracia (EFD) Montería: 7 mujeres jóvenes, 19 mujeres mayores de 28 y 12 hombres jóvenes, total 38 3. NIMD desarrolló dos iteraciones de la Escuela de Democracia Abierta - EDA donde se formaron un total de 71 personas, así: En la primera iteración fueron certificados 31 funcionarios: 11 jóvenes (hombres y mujeres) y 20 mujeres (mayores de 29 años). En la segunda iteración fueron certificados 40 funcionarios: 26 jóvenes (hombres y mujeres) y 14 mujeres mayores de 29. 4. Escuela de Liderazgo y Participación Juvenil para la Incidencia: es una iniciativa financiada por Fondo Acción e implementada por el NIMD, que tiene como objetivo ampliar la capacidad de incidencia social y política para la transformación de las problemáticas ambientales de comunidad y entorno de los adolescentes del Colegio Técnico José Félix Restrepo a través del fortalecimiento de habilidades, capacidades y uso de herramientas prácticas y conceptuales. En este proceso participaron 52 jóvenes de los grados Noveno y Once. 5. Escuela de Acción Comunitaria: Es la iniciativa que surge del convenio entre NIMD y Ecopetrol, en su fase de formación se implementaron tres módulos presenciales sobre introducción al Estado colombiano, enfoque de género, resolución de conflictos, estrategias de diálogo participativo e introducción a la formulación de proyectos así como una fase de una fase de acompañamiento especializado para el diseño de tres proyectos comunitarios, dividida en tres módulos presenciales. En la Escuela participaron y se certificaron 43 personas, así 39 mujeres (16 mujeres jóvenes) y 4 hombres jóvenes. | 300 | Los procesos de formación en NIMD al ser prioritarios por el contexto electoral y de implementación del Mini Public, requirieron el apoyo técnico y metodológico de todo el staff de Power of Dialogue, así como del apoyo financiero, por lo que se reporta nuevamente un número elevado de participantes. De igual forma, se materializó el convenio con Ecopetrol el cual incluía una fase de formación.
Pathway 2 | 2.3 Amplify young voices by nominating themselves for decision-making positions | Outcome Harvest | N/A | N/A | N/A
Pathway 3 | 3.1 Political and civic actors build trust in safe spaces to enable alliances across political or ideological divides for shared agenda development | # of multi-stakeholder dialogue meetings (at sub-national level) | 27 | 1. Se cerró el proceso de Iniciativa de Diálogo Territorial en Buenaventura, orientado a la construcción de propuestas de política pública por parte de la ciudadanía, con los últimos cuatro (4) espacios de diálogo y construcción de la propuesta, pitch e incidencia. 2. Se realizó el proceso de Agenda Ciudadana Territorial en el municipio de Yumbo, una nueva metodología orientada a prototipar soluciones a retos de desarrollo local, construidas por las organizaciones de sociedad civil del departamento del Valle del Cauca, con el objetivo de ser incluidas en planes de gobierno de candidatos, en tres (3) espacios de diálogo y construcción colaborativos. 3. Co-Laboratorio Villavicencio Propone. NIMD implementó un (1) espacio de diálogo colaborativo para que 100 liderazgos realizaran propuestas a las reformas de salud y laboral que se encontraban en trámite en el Congreso. 4. Co-Laboratorio Del Colegio al Congreso. NIMD desarrolló un (1) espacio de diálogo colaborativo de la mano de la Personería de Bogotá y la Cámara de Representantes, donde 71 representantes estudiantiles, entre los 14 y los 18 años, generaron propuestas para mejorar la participación juvenil. 5. Co-Laboratorio Jóvenes por la Paz en Buenaventura. NIMD desarrolló, en alianza con 12 organizaciones de la sociedad civil, un (1) espacio de diálogo colaborativo con 175 jóvenes, orientado a la construcción de propuestas de paz territorial desde la juventud. 6. Co- Laboratorio interno: Ruta 2023 Alianza por la Transformación del Congreso. Este espacio facilitado por NIMD donde participaron 12 organizaciones, pertenecientes a la Alianza por el Congreso. Con el objetivo de propiciar un escenario de diálogo y colaboración, para el establecimiento de un plan estratégico y operativo que incluyera as acciones, cronograma, presupuesto y responsables de la hoja de ruta por cada eje, para el segundo semestre del 2023. 7. Co-Laboratorios La voz de la juventud. Se aplicó la metodología a esta iniciativa del proyecto Quórum en 4 espacios en Bogotá (2), Tolima y Cauca. Con el objetivo de generar espacios de diálogo presencial multiactor con jóvenes para la construcción de insumos para la política pública nacional de juventud. 8. Fase de Deliberación de Mini Public: Esta fase se hizo en dos días con dos encuentros, en el primero se hicieron 10 encuentros temáticos, donde se construyeron las propuestas alrededor del Estatuto de Jóvenes, y que serían discutidas y ampliadas en la siguiente fase del proceso. En el segundo, se reunieron los mismos ejes a formular los planes de acción en un espacio de diálogo presencial en el Congreso con otras organizaciones relevantes para la movilización de las propuestas. 9. En el marco de la construcción del VIII Plan de Acción del Congreso, que se elabora con el apoyo de NIMD y las organizaciones del Eje de Transparencia de la Alianza por el Congreso, se implementó un espacio de diálogo para la co-creación y validación de los compromisos del Plan de la mano de la ciudadanía. 10. El eje de Transparencia de la Alianza por el Congreso de la que NIMD hace parte acompaña la creación del V Plan de Estado Abierto, donde se implementaron 9 Espacios de co-creación en 9 departamentos, denominados Diálogos ciudadanos de la mano de la Secretaría de Transparencia de Presidencia de la República. | 24
Pathway 3 | 3.3 Political and civic actors participate in meaningful dialogue to diagnose and address community grievances at the local level | # of agreements reached (reform agendas / policies / legal amendments) | 6 | 1. En el marco de la Iniciativa de Diálogo de Territorial, 38 liderazgos del Distrito de Buenaventura construyeron un prototipo de política pública con 30 acciones orientadas a resolver problemas de violencia contra jóvenes de la ciudad, que luego fueron socializados con actores relevantes en el distrito y con los candidatos a la Alcaldía. 2. Como resultado de la Agenda Ciudadana Territorial de Yumbo, 68 liderazgos del municipio de Yumbo construyeron un documento con 88 propuestas que fueron relevantes para los programas de gobierno de los 3 candidatos a la Alcaldía. En el marco del trabajo de la Alianza por el Congreso y como parte de la implementación del eje de Transparencia, las organizaciones miembro apoyaron el proceso y la elaboración de los siguientes documentos. 3. VIII Plan de Acción de Congreso, denominado “Para un Congreso Abierto y Transparente”, se encuentra orientado a la implementación de acciones que promueven la participación ciudadana, la lucha contra la corrupción y la transparencia de la institución en relación con la gestión legislativa. Dicho Plan, nace de la necesidad de construir y adoptar procesos que contribuyan a implementar prácticas que promuevan la reducción de los costos económicos y sociales que han generado las deficiencias de las entidades públicas en materia de transparencia y participación y que, adicionalmente, tienen relación con la percepción de legitimidad y confianza que tiene la ciudadanía en la corporación y sus procesos. Adicionalmente, y a través de la Adhesión del Congreso al V Plan de Acción de Estado Abierto, promovido OGP, se alinearon los objetivos del Octavo Plan de Acción a los pilares de trabajo de Gobierno Abierto para contribuir a la armonización de los resultados esperados. 4. V Plan de Estado Abierto, este tiene como objetivo abordar desafíos críticos en áreas como la justicia, la paz, la igualdad de género, los derechos humanos, la lucha contra la corrupción y la gobernanza pública. Es un plan que reafirma un enfoque de Estado, en tanto incluye 23 compromisos en cinco ejes temáticos centrales: Gobernanza pública efectiva para todo el territorio colombiano, Participación ciudadana incidente, Estado Abierto con perspectiva de género, Justicia Abierta, Parlamento Abierto; cuya responsabilidad recae en entidades del ejecutivo del orden nacional y territorial, órganos de control, altas cortes y por primera vez en la historia de la Alianza por el Gobierno Abierto en Colombia (en adelante AGA, y en la rama legislativa desde sus dos cámaras: Senado de la República y Cámara de Representantes. 5. Como producto del Colaboratorio Del Colegio al Congreso con Personería: Como resultado del ejercicio de co-creación y generación de propuestas se lograron diseñar cerca 33 alternativas de solución para responder a las problemáticas priorizadas en el desarrollo del espacio, especialmente, dirigidas al área de medio ambiente y seguridad. Este documento reúne las soluciones con temporalidad, planes de acción y actores identificados. 6. Declaración de Mini Public: Como resultado de la fase de Deliberación, los jóvenes redactaron una declaración donde se comprometían y donde se invitó a las organizaciones asistentes al espacio a comprometerse con apoyar y movilizar propuestas relacionadas con las juventudes y con el ecosistema de participación juvenil. | 6
Pathway 4 | 4.4 Civic and political actors set and lobby a shared agenda on democracy strengthening | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | N/A | 1 | En esta trayectoria se reportan aquellas actividades o procesos que contribuyen en el avance de nuestra relación con los actores priorizados de este trayectoria: Congreso y Ministerio del Interior. Ya que al no existir un proceso de Reforma Política en curso, se prioriza el establecemiento de una relación de asistencia técnica alrededor de la agenda de construcción de Paz, con miras a alcanzar una propuesta efectiva que busque superar las barreras de acceso a la participación de mujeres y jóvenes en temáticas relacionadas con la continuidad del Acuerdo de Paz.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Melissa Zamora
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: En este 2.3 faltan todos los indicadores que sí están expresados en el word.

## Uganda
| Power of Dialogue | Organization: NIMD Uganda
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of agreements reached (reform agendas / policies / legal amendments) | 4 | CSO Agenda setting retreat was held between CSOs and political leaders. A CSO minimum agenda was developed. A total of 31 participants were involved in developing the agenda. (21F, 10M) MYF Leaders met with the Minister of Justice and the Electoral Commission to discuss proposed amendments to the electoral roadmap as well as present 7 electoral reform proposals The MYF secured the partnership of CEPA, and Emmy Otim who both independently agreed to be on the MYF technical team, providing guidauance and techinical support. 3 (1f, 2m) MYF steercom members attended the CEPA meeting | 4
| 1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 6 | 6 Country office staff were trained on how to use the SAGE platform (4F, 2M) | 6
| 1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (youth led) | 8 | 19 CSOs participated in the CSO agenda setting retreat that was used to harmonize organiizational capacities of the various CSO along 4 priority areas for engaging stakeholders. 6 youth organizations were involved in this process. (UPFYA, YAFU, UYONET, NYC, MYF, Raising voices, FARAJA, African Youth Federation) | 3 | Due to the nature of our work, we felt that the inclusion of youth CSOs in the agenda setting was important to ensure that the perspectives of young people were incorporated
| 1.3 PoD Consortium engages in joint L&A at all levels | # of studies for evidence-based L&A disseminated | 2 | A mimimum agenda for women was jointly developed by the leaders of the IWOP, the chairpersons of the womens leagues, CSOs and former members of parliament . During the CSO Agenda Setting Retreat, collaborative discussions took place between Civil Society Organizations (CSOs) and political leaders. The primary outcome was the establishment of a minimum agenda outlined by the CSOs. In the process, a total of 31 participants actively engaged in the development of this agenda, with a gender distribution of 21 females and 10 males. | 1 | The deviation in the study likely arose due to the unique needs and perspectives inherent in both the women's agenda and the Civil Society Organization (CSO) working framework. Harmonizing these elements was essential to optimize project implementation, ensuring a cohesive and well-integrated approach that effectively addresses the distinct requirements of women and aligns with the strategies and objectives of the CSO framework.
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme (youth led) | 8 | 8 Youth led organisations have been included in POD activities including UPFYA, YAFU, UYONET, Raising voices, FARAJA, African Youth FederationUPFYA, YAFU, UYONET, NYC, MYF, Raising voices, FARAJA, African Youth Federation | 2 | In consideration of our work's nature, we recognized the significance of involving youth Civil Society Organizations (CSOs) in the agenda-setting process. This strategic decision aimed to ensure the comprehensive incorporation of young people's perspectives, thereby enhancing the relevance and effectiveness of our initiatives.
| 2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 106 | Monthly fellowships provide a recurring forum for individuals to engage in discussions, network, and share insights on crucial topics, fostering a sense of community and collaboration. The average participation was 81 (40F,41M). Political leaders recently completed a targeted stakeholder engagement and dialogue training, refining skills crucial for effective communication and collaborative decision-making. The training involved 25 participants, consisting of 15 females and 10 males | 150 | The lower attendance in the fellowship was attributed to participant inconsistency and drop-offs, stemming from scheduling conflicts, competing priorities, or unforeseen circumstances. The non-acceptance of the invitation by NUP to participate in our activities also influenced the lower number.
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 10 | A vibrant celebration of International Youth Day unfolded with a lively dialogue and football match, featuring a diverse group of 72 participants. The breakdown comprised 48 males and 24 females, reflecting the inclusive spirit of the occasion. 7 Monthly fellowships offer a platform for young leaders to convene regularly, fostering dialogue and collaboration on critical issues, promoting community building and knowledge-sharing. Topics span diverse areas such as politics, social issues, and personal development. The average participation was 81 (40F,41M). Intergenerational womens dialogue in celebration of the International Women’s Day under the theme of Embrace Equity brought together young leaders and experienced female political leaders to discuss the ways of enhacing effective and meaningful participation of women in the decision making processes of this country. Out of 51 participants, 43 were women and 8 male. The MYF Steering Committee met with CEPA and Emmy Otim on 2 seperate occasions to request them to be part of the MYF Technical Committee 3 participants (1F,2M) and 6 participants (1F, 5M) respectively | 3 | The numbers were more than target because we held 7 monthly fellowships
| 2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at sub-national level) | 2 | As an integral component of the International Youth Day festivities, we orchestrated both a dynamic dialogue session and an exciting football match, involving a collective of 72 participants (24F, 48M). Furthermore, we took deliberate steps to ensure representation from all regions of the country, enhancing the richness and diversity of perspectives shared during this celebratory occasion. The MYF's Youth Day dialogue in Kabale led to invitations for their participation in national celebrations, acknowledging the impact of their initiatives. With a total of 45 participants (15F, 30M), the event exemplified a commitment to fostering diversity and inclusion. | 10 | NIMD held only 1 event in Western Uganda, and incorporated participants from all regions at the youth day match and dialogue. There were no opportunities to go to the regions due to financial constraints
| 2.3 Y&W leaders Amplify diverse young and women voices | # of regional L&A campaigns | 1 | The MYF organized a Youth Day dialogue in Kabale and received invitations to participate in the national celebrations, marking a significant recognition of their contributions and engagement. A total of 45 participants, comprising 30 males and 15 females, took part in the event, reflecting a gender-inclusive and diverse engagement. | 3 | Financial constraints prevent us from meeting target since we could not travel to the regions
Pathway 3 | 3.1 Political and civic actors address grievances | # of multi-stakeholder dialogue meetings (at sub-national level) | 2 | The MYF orchestrated a Youth Day dialogue in Kabale and garnered invitations to the national celebrations, underscoring the recognition of their impactful contributions. A total of 45 participants, (15F, 30M), actively participated, showcasing a commitment to gender-inclusive and diverse engagement. International Youth Day saw us orchestrating a dynamic dialogue session and an invigorating football match, drawing in 72 participants. Deliberate regional representation amplified the event's diversity, with 48 males and 24 females contributing to an inclusive and vibrant atmosphere. | 4 | Financial constraints limited NIMD travel to the regions or of participants to Kampala
| 3.1 Political and civic actors address grievances | # of interparty dialogue meetings (at national level) | 9 | IPOD Breakfast meeting with the leadership of NIMD on the withdrawal of support to IPOD due to challenges related to the inclusion of NUP and reluctance of FDC in signing the new MOU. (6F, 8M) NIMD Leadership also met with political party PWD chairpersons, representatives of women and youth leagues under the IWOP and MYF respectively; to discuss NIMD continued support in empowering aspiring young and women leaders to effectively participate in the politics of this country. There were 8 participants at this meeting (5F, 3M). Anchored in meaningful dialogue and collaboration, 7 monthly fellowships brought together young leaders from political parties for discussions on diverse issues, promoting networking and the free exchange of knowledge within a supportive environment. On average, participation was 81 | 3 | Frequent monthly fellowships increased the number of dialogue engagements
| 3.2 Political and civic actors build trust | # of civic/political actors trained in dialogue/mediation | 25 | Political leaders recently participated in a focused stakeholder engagement and dialogue training, enhancing their skills and fostering effective communication for collaborative decision-making. 25 participants (15F, 10M) | 30 | Some participants cancelled at the last moment
| 3.3 Political and civic actors participate in dialogue | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 81 | In our monthly fellowships, participants converge regularly to exchange ideas, build connections, and explore diverse topics, creating a comprehensive community experience. The average attendance, with 40 females and 41 males, reflects the inclusive and balanced nature of our gatherings. | 70 | We aimed to have about 100 participants at the fellowship and this is why the numbers are more than our target
| 3.4 Political and civic actors attend to root causes | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at sub-national level | 2 | The MYF's Youth Day dialogue in Kabale not only made a significant impact but also secured invitations to the national celebrations, recognizing their valuable engagement. The event drew 45 participants, demonstrating a balanced and inclusive approach with 30 males and 15 females actively participating. During International Youth Day, we organized a vibrant event with a dynamic dialogue session and an exciting football match, engaging 72 participants (24F,48 M). Ensuring representation from all regions enriched the diversity of perspectives, creating an inclusive and vibrant atmosphere. | 5 | Financial constraints limited NIMD travel to the regions or of participants to Kampala
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of created/opened spaces for women/youth (at national level) | 8 | The women's intergrnerational dialoague for the international womens day celebration created an opportunity for both the young and older women to discuss issues afecting their participation in politics. This workshop was attended by 51 participants (43F , 8M) attended this workshop. Rooted in dialogue and collaboration, NIMD held 7 monthly fellowships uniting young leaders across the political spectrum to discuss an array of issues, fostering networking and knowledge exchange within a supportive setting. Attendace was an average of 81 (40F, 41M) | 3 | Frequent monthly fellowships increased the number of spaces

## Kenya
| Power of Dialogue | Organization: Mzalendo Trust, Kenya
Indicator Framework 2023
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Totals Jan-Dec) | Description of actuals (Jan-Dec) | (Adjusted) Targets 2023 | Explanation deviation
Pathway 1 | 1.1 PoD Consortium Works complementary | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 3 | 2 NIMD Meetings at the Hague, 1 planning meting in Mombasa. | 6 | Planned learning sessionsdid not happen perharps due to lack of sychronizing our workplans
| 1.3 PoD Consortium engages in joint L&A at all levels | # of consortium partners/partners/country office members trained | 9 | Online M&E capacity strengthening and support meetings | 9
| 1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 3 | Through our planning meeting in Mombasa, AMwA, Mzalendo Trust and NIMD- Kenya had their capacity strengthened in preparing M&E docs. | 2
| 1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained |  | Indicator dropped, measured through same under 1.3 | 0
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of CSOs with increased organizational capacities (other led) | 25 | 25 CSOs participated in the Bunge Mtaani conversations, Unpacking public participation meeting in Kayole; | 25
| 2.1 Y&W leaders strengthen their movements or organizations | # of political/civic actors taken measures enhancing representation of women and youth | 3 | KYMCA, KYPA, KEWOPA - Together with KYMCA we enhanced our efforts to strengthen youth assemblies to galvanize youth voices at the county level and link them with their elected leaders. In collaboration with KYPA, we had youth Bunge in Parliament's chamber. This collaboration made it possible the tabling of the resolutions of the Youth Bunge in Parliament by the National Assembly's Deputy Speaker. During the induction of KEWOPA which we took part and informed the programme. The association of women parliamentarians committed to advocate for the enactment of the 2/3 gender rule law. | 2
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level |  | Indicator dropped, measured under 2.3 | 0
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of political/civic actors taken measures enhancing representation of women and youth | 7 | The Kenya Young Parliamentarians, represented by 7 young MPs, tabled the youth Bunge resolutions in the National Assembly, 6 Members of different County Assemblies were present during the Coast Regional County Youth Assembly and will oversee the presentation of the resolutions made in respective county assemblies. | 8
| 2.3 Y&W leaders Amplify diverse young and women voices | # of studies for evidence-based L&A disseminated | 1 | The Effects of Technology on Youth Political Participation in Kenya | 1
| 2.3 Y&W leaders Amplify diverse young and women voices | # of interparty dialogue meetings (at national level) | 1 | Interparty dialogue panel during the People's Dialoguie Festival, | 2
| 2.3 Y&W leaders Amplify diverse young and women voices | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 7 | A community dialogue in Kisii County; KEWOPA Induction; WPP Scorecard 2023 – Pausing, Reflecting & Re-strategizing Transformative Women’s Political Leadership in Kenya (Thematic Dialogue with Women Parliamentarians in Kenya); Bunge Youth Dialogue, Coast Regional Youth Assembly, International Democracy Day -empowering the next generation through digital platforms; Bunge Mtaani Conversations - on leveraging public Young women, Youth and grassroots communities in public participation processes | 15 | 15 activities might have been too ambitious
Pathway 4 | 4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 2 | Panel participation in “The Future is African – a Case Study”; Moderated a panel on Misinformation, Disinformation and Propaganda Machines on the Democratic Process during the AU ECOSOCC Annual Citizens' Forum focusing on Democracy and Digital Governance | 2
| 4.1 Regional and int. bodies promote and protect democracy | # of multi-stakeholder dialogue meetings (at international level) | 2 | Athens Democracy Forum, co-hosted with The New York Times and themed “Do We Dare to Hope? ; participated in The Africa Drive for Democracy Summit, Elders Conference held in Arusha - Tanzania | 1
| 4.2 Civic and political actors safeguard civic space | # of multi-stakeholder dialogue meetings (at national level) | 3 | Participated in the National Okoa Uchumi dialogue; Participated in the National Dialogue on Gender and Leadership; Participated in a panel on “Taking Stock of the Democratic Gains and Loses Post-2010 Constitution” ; | 3
| 4.2 Civic and political actors safeguard civic space | # of agreements reached (reform agendas / policies / legal amendments) | 2 | Withdrawal of laws that dilute anti-graft legal framework; Multi-Sectoral Working Group on the realization of two-thirds gender principle created | 1
| 4.3 Civic and political actors adhere to democratic rules | # of studies for evidence-based L&A disseminated | 3 | 1 policy brief on "Intersection between data, dialogue and accountability; Supporting Development of KYMCA Strategic Plan, Analysis of the Finance Bill. | 4 | The transitions brought about a huge workload and it was difficult to develop policy briefs internally.
| 4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at national level) | 5 | The Inaugural Session of The Parliamentary Caucus on SDGs and Business; Launch of the Human Rights and Democracy Caucus; Media roundtable with APNAC; Meeting with the public service on strategies to fight corruption; Mzalendo and CSPEN submit 17 bills | 4
| 4.4 Civic and political actors set shared policy agendas | # of political/civic actors taken measures enhancing representation of women and youth | 2 | Mzalendo supports the development of a safeguarding policy on sexual misconduct in parliament, The cabinet Secretary of Gender receives a memorandum on the 2/3 gender rule from CSPEN | 4 | 4 might have been a high target

## Ethiopia
| Power of Dialogue | Organization: NIMD Ethiopia
Indicator Reporting template
| (Intermediate) outcome statement | (intermediate) outcome indicator | Actuals 2023 (Jan-December) | Description | Target 2023 | Explanation deviation
Pathway 1 | 1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 20 | 1. 8 participants ( 5 M, 3 F) drawn from NIMD regional staff, Electoral Management bodies, Civil Society organizations, and Non-Government organizations attended a 10-day Bridge Train the Facilitator (TTF) Training from May 28– 7, 2023, at the Sapphire Addis Hotel, Addis Ababa, Ethiopia, on Facilitation Skills and relevant electoral modules. 2.NIMD held a retreat for 12 staff (6 female) and NGSS staff ( from July 7-9, 2023 at Kuriftu Resort, Bishoftu. The retreat aimed to recharge and strengthen team dynamics through team-building activities and workshops. It fostered collaboration and communication, leading to increased productivity and a more cohesive work environment. The retreat included experience sharing, presentations on staff achievements, challenges and lesson learned, team-building exercises, and interactive engagements fostering camaraderie and trust among employees. It aimed to create a positive work culture that values teamwork, continuous learning, and mutual support. | 200 | The target was ambitious and had already been adjusted to 20 for the year 2024.
Pathway 2 | 2.1 Y&W leaders strengthen their movements or organizations | # of political/civic actors taken measures enhancing representation of women and youth | 0 | During this period, There is no political/civic actors that has taken measures that enhances representation of women and youth | 7
| 2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 12 (6F) | 1. As per the agreement or understanding among the EDAC alumni on the need to establish an EDAC Alumni Association or Network at various EDAC-related meetings, NIMD conducted preparatory work or a planning phase to commence a consultation workshop among coordinators of each EDAC round on the modalities and procedures that could be followed to establish an association and network, plus to discuss and establish a small member committee that can be drawn from the coordinators and take the lead in coordinating and mobilizing the coordinators and pushing forward the agenda of establishing an association or network. As guidance for their consultation, CGSS and NIMD political advisor delivered a short training session on effective networking strategies and best practices for establishing associations and networks. This training aimed to equip coordinators with the necessary skills and knowledge to successfully navigate the process of forming an association or network within the EDAC community. | 50 | We had a plan to train youth and women in consultation with the women and youth wing of the Ethiopian Political Party Joint Council. However, due to their internal bureaucracy, they were not ready. That is why the number difference exists.
| 2.3 Y&W leaders Amplify diverse young and women voices | # of agreements reached (reform agendas / policies / legal amendments) | 2 | NIMD held an EDAC alumni network event at the InterLuxury Hotel in 2023, featuring 36 participants, including 16 females. Due to budget constraints, NIMD invited only committee members/coordinators from each EDAC round, including those from different political parties and regions. The event allowed coordinators to network for the first time, promoting mutual discussions and discussed on the importance of an alumni network, its coordination, its potential benefits, including collaboration and knowledge-sharing among members. A common Telegram channel was proposed for the purpose of sharing important updates and information with the community and to serve as a platform for members to engage in discussions and exchange ideas. An interim committee of members was elected to coordinate alumni activities and lead the process of establishing the Alumni Network. | 1
| 3.1 Political and civic actors address grievances | # of multi-stakeholder dialogue meetings (at national level) | 1 | On June 1, 2023, The Ethiopian Political Parties Joint Council undertook its General Assembly and had discussion among 53 representatives of different National and Regional level political parties on the report prepared on the exchange visit that happened in Northern Ireland, relationships with partners, and Current issues in the country. | 1
| 3.2 Political and civic actors build trust | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office |  |  | 60
| 3.2 Political and civic actors build trust | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office |  | No Activities done for this indicator! | 1
| 3.2. Political and civic actors build trust | # of civic/political actors trained in dialogue/mediation | 12 | The Netherlands Institute for Multi-party Democracy (NIMD) organized a peer-learning exchange visit to South Africa for 12 Ethiopian politicians ( 1 female) from December 3 to 8, 2023. The visit aimed to learn from South Africa's experience in political transition, mediation, dialogue, and compromises. The delegation met with Prof. Zwelethu Jolobe, Prof. Jaap de Visser, and the ANC Caucus, discussing the ANC's history and transition from apartheid to democracy. They also met with DA National Leader John Steenhuisen and their team at Parliament of South Africa, discussing the party's unique position and pact with opposition parties. | 60 | The training is based on need. And our stakeholders were not ready to arrange training.
| 3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (other led) | 2 | Authoriy for Civil Society Organizations (ACSO) and Ethiopian Political Parties Joint Council (EPPJC) | 1
Pathway 4 | 4.2 Civic and political actors safeguard civic space | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 2 | 1. With the objective of improving transparency and accessibility, NIMD supported the development of a mobile application called BRIDGE (Bridging Research and Innovation for Democratic Governance and Enhanced Participation—BRIDGE for Participation) under the project called "Enhancing Participation through an E-Democracy Platform for Members of Caffee and Citizens in Ethiopia." The mobile app is in different languages (Afaan Oromo, Amharic, and English) and are ready to be used by Caffee Oromia for the purpose of sharing reports, proclamations, and minutes with the 504 caffe members, data capturing, communication, staff interaction, and connecting the caffee members with their constituents. The mobile application has a version of Websites where there is an admin page for Caffe to administer the website. The websites incorporated sections like about caffe, calendar of events, laws of the council (in languages of Afaan Oromo, Amharic, and English), and profiles of all members of Caffee as well as a section where Constituents can ask questions to the MPs 2. As part of building the full monitoring and evaluation system of the HoPR, NIMD supported the HoPR starting from the preparatory works until the automation, such as an introduction meeting for HoPR experts to discuss the data collection tools and methodology of the baseline survey, which is the prior phase of automation, the development of tools for conducting surveys, and the actual work of the survey. Apart from that, the foundation for automation, which includes the design of SPSS, data entry and analysis, and the baseline report, is done, and the system is now being automated. As part of the automation, data encoding is completed, and the results of the system, such as report generation, are already tested. Once the automation is completed and the system starts to operationalize. | 10
| 4.3 Civic and political actors adhere to democratic rules | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | Nothing was implemented for this indicator. | 60 | Nothing is planned for this for the year 2024.
| 4.4 Civic and political actors set shared policy agendas | # of studies for evidence-based L&A disseminated | 0 | Nothing was implemented for this indicator. | 0 | Nothing is planned for this for the year 2024.

## Example (hidden)
|  | Power of Dialogue | Organisation: XXXX
|  | Planning, Monitoring and Evaluation Framework | Country: XXXXX
Pathway 1 |  | Outcome Indicators |  | Pathway 2 |  | Outcome Indicators
| 1.Consortium partners (NIMD & AMwA) and XXXX are effective enablers of change | # international L&A resolutions on democratic space adopted |  |  | 2. Aspiring and elected young and women are influential actors of change within CSOs targeting youth and women, political party youth leagues, parliament and county assemblies | # of women and youth involved in politics who feel they are able to participate in decision-making processes
|  | Intermediate / output indicators | Types of interventions |  |  | Intermediate / output indicators | Types of interventions
| 1.1 Engage in joint planning, pool resources, coordinate communication messages (joint events), organize joint M&E and learning | # of consortium partners/partners/country office members trained | Organisational capacity building activities |  | 2.1 Strengthen their capacity to organize and mobilize resulting in increased participation and impact in political processes | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | Skills training for young and women leaders (“democracy school”)
# of women/youth leaders trained
| 1.2 Builds each other’s organizational capacity and leverage each other’s networks’ | # of CSOs with increased organizational capacities | Peer learning around use of social media/technology, use of infographics, leveraging reg. And global networks |  | 2.2 Lobby and advocate for youth and women participation in decision making to hold leadership roles in parliamentary and county committees | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) | Sensitize party leaders on youth and women political participation through research-informed advocacy .
# of studies for evidence-based L&A disseminated
| 1.3 Participate in L&A training and develop a joint lobby and advocacy strategy for shared policy goals | # of consortium partners/partners/country office members trained | Training on L&A |  | 2.3 Unite, showcase and amplify diverse young and women voices within parliament and county assemblies | Outcome Harvesting | Use online outreach tools to showcase the work of young and women voices/experiences
This example is adapted from an existing country programme PoD ToC. Please note the contextualized intermediate outcome and outcome statements, also interventions and indicators have been added. For this example just pathways 1 and 2 are worked out.