## Mozambique
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 8 | 11 | There are no significant deviations. The deviations do not have any particular reason.
1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 1 | 1 | Idem
2.1 Y&W leaders strengthen their movements or organizations | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 2 | 2 | Idem
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 140 | 140 | Idem
3.1 Political and civic actors address grievances | # of political/civic actors taken measures enhancing representation of women and youth | 5 | 3 | Idem
3.1 Political and civic actors address grievances | # of agreements reached (reform agendas / policies / legal amendments) | 0 | 0 | Idem
3.2 Political and civic actors build trust | # of interparty dialogue meetings (at national level) | 3 | 1 | Idem
3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (women led) | 2 | 3 | Idem
4.1 Regional and int. bodies promote and protect democracy | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 4 | 3 | Idem
4.2 Civic and political actors safeguard civic space | # of multi-stakeholder dialogue meetings (at national level) | 3 | 1 | Idem

## Ethiopia
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 100 | 86 | Not all planned capacity building activities have been implemented due to the crisis in Ethiopia and coordination issues
2.1 Y&W leaders strengthen their movements or organizations | # of political/civic actors taken measures enhancing representation of women and youth | 7 | 0 | 47 Political Parties have been trained on the need of women and youth inclusion, and will be further trained over the course of the programme, yet actual measures have not been taken bij PP
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 20 | 0 | Trainings have happened but budgeted under another project
2.3 Y&W leaders Amplify diverse young and women voices | # of agreements reached (reform agendas / policies / legal amendments) | 1 | 1
3.1 Political and civic actors address grievances | # of multi-stakeholder dialogue meetings (at national level) | 0 | 1
3.2 Political and civic actors build trust | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 1 | 1
3.2 Political and civic actors build trust | # of civic/political actors trained in dialogue/mediation | 25 | 0 | Have not implemented due to security restrictions
3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (other led) | 2 | 0
4.2 Civic and political actors safeguard civic space | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 5 | 0 | The idea was to include at least one more regional legislature and one additional democratic institution (DI). Nonetheless, due to the security situation, the state of emergency and other administrative matters, this target has not materialized.
4.3 Civic and political actors adhere to democratic rules | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 20 | 37

## Kenya
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 8 | 10 | This target was fully achieved.
1.2 PoD Consortium builds capacities | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 4 | 0 | This has not been achieved in 2021.
1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 20 | 0 | This is not achieved yet, since it was an L&A training. It set to happen in 2022.
1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 3 | 4 | This target was fully achieved.
1.3 PoD Consortium engages in joint L&A at all levels | # of consortium partners/partners/country office members trained | 1 | 0 | This target has been set for 2022.
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs with increased organizational capacities (other led) | 6 | 5 | This target was partially achieved.
2.1 Y&W leaders strengthen their movements or organizations | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | 0
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 13 | 13 | This target was fully achieved.
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of political/civic actors taken measures enhancing representation of women and youth | 3 | 2 | This target was partially achieved.
2.3 Y&W leaders Amplify diverse young and women voices | # of studies for evidence-based L&A disseminated | 2 | 2 | This target was fully achieved.
2.3 Y&W leaders Amplify diverse young and women voices | # of interparty dialogue meetings (at national level) | 3 | 3 | This target was fully achieved.
2.3 Y&W leaders Amplify diverse young and women voices | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 1 | 1 | This target was fully achieved.
4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 5 | 5 | This target was fully achieved.
4.1 Regional and int. bodies promote and protect democracy | # of multi-stakeholder dialogue meetings (at international level) | 4 | 6 | This target was fully achieved.
4.2 Civic and political actors safeguard civic space | # of multi-stakeholder dialogue meetings (at national level) | 4 | 4 | This target was fully achieved.
4.2 Civic and political actors safeguard civic space | # of agreements reached (reform agendas / policies / legal amendments) | 3 | 3 | This target was fully achieved.
4.3 Civic and political actors adhere to democratic rules | # of studies for evidence-based L&A disseminated | 6 | 1
4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at national level) | 6 | 6 | This target was fully achieved.
4.4 Civic and political actors set shared policy agendas | # of political/civic actors taken measures enhancing representation of women and youth | 8 | 10 | This target was fully achieved.

## Uganda
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of agreements reached (reform agendas / policies / legal amendments) | 2 | 0
1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 13 | 10
1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (youth led) | 1 | 1
1.3 PoD Consortium engages in joint L&A at all levels | # of studies for evidence-based L&A disseminated | 1 | 1
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme (youth led) | 0 | 1
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 190
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 2 | 2
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at sub-national level) | 2 | 2
2.3 Y&W leaders Amplify diverse young and women voices | # of regional L&A campaigns | 2 | 0
3.1 Political and civic actors address grievances | # of multi-stakeholder dialogue meetings (at sub-national level) | 10 | 2
3.1 Political and civic actors address grievances | # of interparty dialogue meetings (at national level) | 10 | 8
3.2 Political and civic actors build trust | # of civic/political actors trained in dialogue/mediation | 20 | 0
3.3 Political and civic actors participate in dialogue | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 50 | 0
3.4 Political and civic actors attend to root causes | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at sub-national level | 5 | 0
4.1 Regional and int. bodies promote and protect democracy | # of created/opened spaces for women/youth (at national level) | 2 | 3

## Sahel (Goree)
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 20 | 0 | Most actuals were on track, no specific explanations for the deviation are given
1.2 PoD Consortium builds capacities | # of CSOs included in the PoD programme (women led) | 10 | 18
1.2 PoD Consortium builds capacities | # of CSOs included in the PoD programme (youth led) | 15 | 25
1.3 PoD Consortium engages in joint L&A at all levels | # of CSOs with increased organizational capacities (women led) | 20 | 18
1.3 PoD Consortium engages in joint L&A at all levels | # of CSOs with increased organizational capacities (youth led) | 20 | 39
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 150 | 117
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 5 | 7
3.1 Political and civic actors address grievances | # of studies for evidence-based L&A disseminated | 3 | 1
3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at regional level) | 3 | 3
4.1 Regional and int. bodies promote and protect democracy | # of studies for evidence-based L&A disseminated | 1 | 1
4.2 Civic and political actors safeguard civic space | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at regional level | 1 | 3
4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at regional level) | 5 | 6

## Horn of Africa (AMwA)
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of agreements reached (reform agendas / policies / legal amendments) | 1 | 0
1.1 PoD Consortium Works complementary | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 4 | 20
1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 27 | 27 | The activities that consortium partners staff participated in include Gender Transformative Training, African Women Leadership Institute(AWLI), MEL training, Advocacy training.
1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (youth-led). | 1 | 0 | Training will be conducted in 2022
1.3 PoD Consortium engages in joint L&A at all levels | # of consortium partners/partners/country office members trained | 0 | 0 | L&A strategy training will take place in 2022
1.3 PoD Consortium engages in joint L&A at all levels | # of studies for evidence-based L&A disseminated | 0 | 2 | PEA and baseline
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 300 | 57 | Only 57 youth/women leaders trained in Uganda
2.1 Y&W leaders strengthen their movements or organizations | # of political/civic actors taken measures enhancing representation of women and youth | 0 | 0
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme (youth led) | 0 | 1 | Interparty Youth Platform was reached in the POD programme.
2.1 Y&W leaders strengthen their movements or organizations | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | 0
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of political/civic actors taken measures enhancing representation of women and youth | 0 | 3 | Political actors who include Democratic Party, Forum for Democratic Change, National Unity Platform & Peoples’ Progressive Party took measures enhancing the representation of women and youth was achieved. Democratic party developed Gender policies.
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 0 | 2 | 2 spaces were created for women/youth at subnational level which include Intergenerational dialogue(NOWIP) & IYOP spaces.
4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 | 0
4.1 Regional and int. bodies promote and protect democracy | # of multi-stakeholder dialogue meetings (at national level) | 0 | 0
4.2 Civic and political actors safeguard civic space | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 0 | 0
4.2 Civic and political actors safeguard civic space | # of multi-stakeholder dialogue meetings (at national level) | 0 | 0
4.2 Civic and political actors safeguard civic space | # of agreements reached (reform agendas / policies / legal amendments) | 0 | 0
4.4 Civic and political actors set shared policy agendas | # of studies for evidence-based L&A disseminated | 0 | 0
4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at international level) | 0 | 0
4.4 Civic and political actors set shared policy agendas | # of political/civic actors taken measures enhancing representation of women and youth | 0 | 0

## Guatemala
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 20 | 31 | There are no specific explanations given for the deviation, all implementation was well on track
1.2 PoD Consortium builds capacities | # of CSOs with increased organizational capacities (other led) | 0 | 0
3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (women led) | 2 | 3
3.2 Political and civic actors build trust | # of CSOs included in the PoD programme (other led) | 30 | 61
3.2 Political and civic actors build trust | # of interparty dialogue meetings (at national level) | 10 | 16
3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at national level) | 8 | 13
3.4 Political and civic actors attend to root causes | # of women/youth leaders trained | 30 | 58
4.4 Civic and political actors set shared policy agendas | # of studies for evidence-based L&A disseminated | 3 | 3

## Colombia
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 900 | 837 | The trainings happened over several events in 2021, was hard to predict the exact number of participants. Difference is not significant
3.1 Political and civic actors address grievances | # of multi-stakeholder dialogue meetings (at sub-national level) | 0 | 43 | Opportunities for dialogue presented themselves in occurance of National Strike (as a result of tax reform to tackle inflation and unemployment) and Land Management Plan project
3.3 Political and civic actors participate in dialogue | # of agreements reached (reform agendas / policies / legal amendments) | 0 | 16 | Agreements followed out of the dialgoue intervention around the land management plan project

## Mali
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0 | 1 | A stakeholder statement was made to the African Union Commission (AUC) (See Statement) This is the beginning of a sub-regional lobbying process to ensure better ownership of the principles and ideals that underpin these mechanisms of the African Union.
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5 | 0 | Gender audit did not take place
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5 | 5 | No (significant) deviation that can be explained
1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 6 | 6 | Idem
1.3 PoD Consortium engages in joint L&A at all levels | # of regional L&A campaigns | 0 | 0 | Idem
1.3 PoD Consortium engages in joint L&A at all levels | # of studies for evidence-based L&A disseminated | 3 | 3 | Idem
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 120 | 60 | instead of chaining the schools, the NIMD took the time to evaluate the implementation of the first promotions by reviewing the curricula , the pedagogy as well as the pool of trainers.
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | 0 | No (significant) deviation that can be explained
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 0 | 0 | Idem
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 1 | 1 | Idem
3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 0 | 0 | Idem
3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at national level) | 9 | 10 | Idem
3.4 Political and civic actors attend to root causes | # of studies for evidence-based L&A disseminated | 3 | 2 | Idem
3.4 Political and civic actors attend to root causes | # of CSOs included in the PoD programme (other led) | 7 | 9 | Idem
4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 | 0 | Idem

## Burkina Faso
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5
1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 6
1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 3 | 1 | PEA
1.3 PoD Consortium engages in joint L&A at all levels | # of regional L&A campaigns | 0
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 110 | 110 | The results achieved show 40 young people (girls and boys) trained within the framework of Democratic and Popular Universities/Political Schools; 50 women saw their leadership capacities strengthened within the framework of the project implemented with the CBDF and 20 young people were trained within the framework of the project implemented with the ABB. | The planned objectives were achieved in terms of the number of people to be trained. But at the level of the ABB, there remains the animation of blogs by the young girls trained. The delay in the execution of the project at ABB partly explains this.
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | 1
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at regional level) | 0
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 1 | 3 | In terms of results, activities were organized to amplify the voices of women and young people: 2 radio programs with the CBDF, a debate competition between young people and two conferences with Semfilms . With the ABB, a training session was organized to equip young girls with blog creation techniques, web writing and personal social media branding . Without forgetting the creation of 3 frameworks for exchanges between young girl leaders and emerging female political figures.
3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 0
3.3 Political and civic actors participate in dialogue | # of multi-stakeholder dialogue meetings (at national level) | 6 | 6 | During the year, plans were made to set up consultation frameworks in Dori and Ouagadougou following the inclusive political dialogues. With ARGA, the NIMD organized 2 political cafés which brought together political actors, researchers, representatives of the State and citizens. With Semfilms , 2 democratic dialogues were also organized on democracy and the future of the country. These dialogues are meant to be spaces for fruitful reflection on democracy and the issues at stake for the populations.
3.4 Political and civic actors attend to root causes | # of studies for evidence-based L&A disseminated | 0
3.4 Political and civic actors attend to root causes | # of CSOs included in the PoD programme (other led) | 5 | 6 | · The interventions here are linked to the involvement of CSOs in the programme. The CSOs in question are: Balai Citoyen and Semfilms , Anndal Institute, the Burkinabè Coalition for Women's Rights and the Association of Bloggers of Burkina. A sixth CSO has been included in the program as part of the organization of Political Cafés: ARGA.
4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0
It only appears that certain partners initially targeted could not be contacted. These include, for example, the University Clubs and the MysTIC association . Also, the partnership with Semfilms, which was to consist of setting up a digital platform, ultimately focused more on the organization of democratic dialogues. We can also note the weak participation of leading political leaders in the various activities. This can be explained on the one hand by the extremely busy political calendar after the 2020 presidential election, and on the other hand by the sluggishness of relations with these actors due to changes within the team as well as a problem of human ressources. This situation will be corrected during the year 2022 thanks to additional efforts in dialogue with political actors.

## Niger
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of regional L&A campaigns | 0 | 0 | No expanations given
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5 | 0
1.1 PoD Consortium Works complementary | # of consortium partners/partners/country office members trained | 5 | 0
1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 6 | 1
1.2 PoD Consortium builds capacities | # of studies for evidence-based L&A disseminated | 3 | 0
1.3 PoD Consortium engages in joint L&A at all levels | # of regional L&A campaigns | 0 | 0
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 30 | 53
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 0 | 1
2.3 Y&W leaders Amplify diverse young and women voices | # of created/opened spaces for women/youth (at national level) | 0 | 6
3.3 Political and civic actors participate in dialogue | # of political/civic actors taken measures enhancing representation of women and youth | 0 | 1
4.1 Regional and int. bodies promote and protect democracy | # of regional L&A campaigns | 0 | 0

## Myanmar
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of CSOs included in the PoD programme (other led) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
1.2 PoD Consortium builds capacities | # of civic/political actors trained in dialogue/mediation | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
2.1 Y&W leaders strengthen their movements or organizations | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
2.1 Y&W leaders strengthen their movements or organizations | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 0 | 10 | Mysop managed to carry out preparation activities, including outreach, revising curriculum, devolop and test Link and Learn platform, etc.
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
2.3 Y&W leaders Amplify diverse young and women voices | # of multi-stakeholder dialogue meetings (at sub-national level) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
3.1 Political and civic actors address grievances | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at sub-national level) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
3.2 Political and civic actors build trust | # of agreements reached (reform agendas / policies / legal amendments) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
3.3 Political and civic actors participate in dialogue | # of interparty dialogue meetings (at sub-national level) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
3.4 Political and civic actors attend to root causes | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
4.2 Civic and political actors safeguard civic space | # of preparation activities to create/consolidate operational space for the consortium partner/partner/country office | 0 | 5 | Liaise activities with alumni, CSOs, L&A networks, etc.
4.2 Civic and political actors safeguard civic space | # of CSOs included in the PoD programme (other led) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.
4.4 Civic and political actors set shared policy agendas | # of multi-stakeholder dialogue meetings (at national level) | 0 | 0 | Due to programme re-strategizing as a result of political instability, there were no interventions carried out under this activity in 2021.

## Jordan
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.1 PoD Consortium Works complementary | # of multi-stakeholder dialogue meetings (at international level) | 4 | 4 | There are no significant deviations. The deviations do not have any particular reason.
1.2 PoD Consortium builds capacities | # of consortium partners/partners/country office members trained | 2 | 2 | Idem
2.1 Y&W leaders strengthen their movements or organizations | # of women/youth leaders trained | 100 | 118 | Idem
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at sub-national level | 2 | 2 | Idem
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 7 | 7 | Idem
2.3 Y&W leaders Amplify diverse young and women voices | # of agreements reached (reform agendas / policies / legal amendments) | 3 | 5 | Idem
3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at national level) | 8 | 8 | Idem
3.2 Political and civic actors build trust | # of multi-stakeholder dialogue meetings (at sub-national level) | 3 | 3 | Idem
4.2 Civic and political actors safeguard civic space | # of CSOs included in the PoD programme (women led) | 0 | 0 | Idem
4.2 Civic and political actors safeguard civic space | # of CSOs included in the PoD programme (youth led) | 3 | 3 | Idem
4.2 Civic and political actors safeguard civic space | # of agreements reached (reform agendas / policies / legal amendments) | 4 | 5 | Idem
4.4 Civic and political actors set shared policy agendas | # of L&A activities for making the political system more inclusive (in relation to women / youth / minority groups) at national level | 4 | 4 | Idem

## Tunisia
Intermediate outcome | Indicator | Target 2021 | Actual 2021 | Explanation
1.3 PoD Consortium engages in joint L&A at all levels | # of international L&A campaigns | 0 | 0 | L&A capacity still needed
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs with increased organizational capacities (youth led) | 3 | 7
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme (youth led) | 3 | 3
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs with increased organizational capacities (women led) | 5 | 2
2.1 Y&W leaders strengthen their movements or organizations | # of CSOs included in the PoD programme (youth led) | 5 | 7
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 65 | 79
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 101 | 73
2.2 Y&W leaders lobby and advocate in decision-making spaces | # of women/youth leaders trained | 7 | 41
2.3 Y&W leaders Amplify diverse young and women voices | # of women/youth leaders trained | 7 | 41
2.3 Y&W leaders Amplify diverse young and women voices | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 17 | 33
3.2 Political and civic actors address grievances | # of agreements reached (reform agendas / policies / legal amendments) | 4 | 3
3.2 Political and civic actors address grievances | # of civic/political actors trained in dialogue/mediation | 100 | 329
3.1 Political and civic actors build trust | # of interparty dialogue meetings (at national level) | 8 | 9
3.1 Political and civic actors build trust | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 100 | 237
3.3 Political and civic actors participate in dialogue | # of interparty dialogue meetings (at national level) | 12 | 13
4.2 Civic and political actors safeguard civic space | # of created/opened spaces for women/youth (at national level) | 2 | 4
4.1 Civic and political actors adhere to democratic rules | # of representatives (male/female) of political actors have participated in democratic values oriented training activities (e.g. democracy schools | 70 | 292