## Financial Report DfS 2020
Financial Report 2020 DfS NIMD
|  | Original Budget | Updated Budget | Updated Budget | Actuals |  |  |  | Original Budget | Updated Budget | Original Budget | Updated Budget | Original Budget | Updated Budget | Actuals
|  | 2020 | [5 empty] | Notes | 2019 |  | 2020 |  | 2016-2020
I - | Programmes | [7 empty] | 2019 |  | 2020 |  | 2016-2020
1. | Dialogue for Stability country programmes
1.1 | Burundi
| Objective 1 (System) | 24677.4542 | 55006.8327 | 53325.6126 | 16966.6211 |  | 31.82% | The underspending on objective 1 and 4 are due to difficulties in implementing interventions at national level. The funds were shifted to support sub-national interventions at provincial level (see section 2 of the narrative report). The programme monitoring budget, which includes NIMD missions and travel costs, was drastically reduced in the revised annual plan but still could not be spent due to COVID-19 restrictions. The capacity building activities for PM&E could not be implemented for the same reasons (support was provided online). | 24677.4542 | 49162 | 25947.3472 |  | #REF! | #REF!
| Objective 2 (Actor) | 104069.492 | 0 | 0 | 0 |  | 0% |  | 104069.492 | 43000 | 72976.395 |  | #REF! | #REF!
| Objective 3 (Culture) | 51594.78 | 54292.5836 | 52635.533 | 140294.6944 |  | 266.5% |  | 51594.78 | 124274 | 36166.043 |  | #REF! | #REF!
| Objective 4 (Gender equality & Inclusion) | 476.7657 | 54292.5836 | 52630.8544 | 11869.9961 |  | 22.55% |  | 476.7657 | 15128 | 502.2098 |  | #REF! | #REF!
| Programme monitoring | 16937.195 | 16937 | 4000 | 206.24 |  | 5.156% |  | 16937.195 | 16937 | 16937.195 |  | #REF! | #REF!
| Capacity building for PM&E | 19000 | 19000 | 19000 | 0 |  | 0% |  | 19000 | 19000 | 19000 |  | #REF! | #REF!
| Local Office Costs Partner/Country Office | 42749.631 | 15000 | 20000 | 20508.9284 |  | 102.5% |  | 42749.631 | 20000 | 42749.631 |  | #REF! | #REF!
| Total country budget | 259505.3179 | 214529 | 201592 | 189846.48 | 11745.52 | 94.17% |  | 259505.3179 | 287501 | 214278.821 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD | 46080 | 59181.3474 | 59181.3474 | 66798 |  | 112.9% |  | 46080 | 72459.8 | 46080 |  | #REF! | #REF! | #VALUE!
| Total Budget | 305585.3179 | 273710.3474 | 260773.3474 | 256644.48 | 4128.8674 | 98.42% |  | 305585.3179 | 359960.8 | 260358.821 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.2 | Colombia
| Objective 1 (System) | To be decided | 39962.3265 | 39962.3265 | 51325.8622 |  | 128.4% | The NIMD Colombia office made use of part of the underspending of the Venezuela budget (managed through Colombia) to implement additionnal interventions on objective 1, 2 and 4. The underspending on objective 3 is due to the fact that Democracy School sessions were implemented online until the end of the year. The programme monitoring budget, which includes NIMD missions and travel costs, could not be spent due to COVID-19 restrictions. The capacity building activities for PM&E could not be fully implemented for the same reasons (support was provided online). On local office costs there were some savings, mainly related to the rent. | To be decided | 32487.3901 | To be decided
| Objective 2 (Actor) |  | 25899.7876 | 25899.7876 | 43175.292 |  | 166.7% |  |  | 43497.7608
| Objective 3 (Culture) |  | 30841.5927 | 30841.5927 | 20896.3023 |  | 67.75% |  |  | 97869.9618
| Objective 4 (Gender equality & Inclusion) |  | 28150.4132 | 28150.4132 | 42261.7571 |  | 150.1% |  |  | 38060.5407
| Programme monitoring |  | 7500 | 7500 | 1147.69 |  | 15.3% |  |  | 7500
| Capacity building for PM&E |  | 10000 | 10000 | 6696.9697 |  | 66.97% |  |  | 19000
| Local Office Costs Partner/Country Office |  | 47600.0009 | 47600.0009 | 41672.9366 |  | 87.55% |  |  | 24900
| Total country budget | 219000 | 189954.1209 | 189954.1209 | 207176.81 | -17222.6891 | 109.1% |  | 219000 | 263315.6533 | 219000 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD | 38720 | 40519.9579 | 40519.9579 | 34570 |  | 85.32% |  | 38720 | 52891.4 | 38720 |  | #REF! | #REF! | #VALUE!
| Total Budget | 257720 | 230474.0788 | 230474.0788 | 241746.81 | -11272.7312 | 104.9% |  | 257720 | 316207.0533 | 257720 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.3 | South Sudan
| conference | [8 empty] | 0
| peer exchange | [8 empty] | 0
| Programme monitoring | [8 empty] | 0
| Capacity building for PM&E | [8 empty] | 0
| Total country budget | 58000 | 0 | 0 | 0 | 0 | 0% |  | 58000 | 0 | 58000 | 0 | #REF! | #REF!
| Direct Staff Costs NIMD | 23280 |  |  | 0 |  |  |  | 23280 | 0 | 23280 |  | #REF! | #REF!
| Total Budget | 81280 | 0 | 0 | 0 | 0 | 0% |  | 81280 | 0 | 81280 | 0 | #REF! | #REF! |  | #REF!
1.4 | Tunisia
| Objective 1 (System) | 24823.3967 | 89063.9936 | 80123.9847 | 67354.2305 |  | 84.06% | The overall programmatic underspending is due to the fact that a number of planned interventions with high level political actors, such as the MDP (objective 1) and the TSoP debates (objective 3), could not be implemented due to a difficult national political context (see section 2 of the narrative report). The programme monitoring budget, which includes NIMD missions and travel costs, was reduced in the revised annual plan but still could not be spent due to COVID-19 restrictions. The capacity building activities for PM&E could not be implemented for the same reasons (support was provided online).The underspending on PM&E is due to the fact that CEMI conducted the final measurements of outcome level indicators in-house, instead of getting support from an external consultant as initially foreseen. Finally, NIMD staff costs were lower than foreseen, because the focus of the collaboration with CEMI was on the development on the new Power of Dialogue programme, rather than the Tunisia DfS one. | 24823.3967 | 93676.4296 | 24823.3967 |  | #REF! | #REF!
| Objective 2 (Actor) | 79888.3672 | 101378.3363 | 96020.0229 | 79605.5982 |  | 82.91% |  | 79888.3672 | 124219.0201 | 79888.3672 |  | #REF! | #REF!
| Objective 3 (Culture) | 42501.3508 | 9159.0267 | 8593.5446 | 1666.6661 |  | 19.39% |  | 42501.3508 | 10683.429 | 42501.3508 |  | #REF! | #REF!
| Objective 4 (Gender equality & Inclusion) | 0 | 7522.9439 | 7380.808 | 6956.4449 |  | 94.25% |  | 0 | 11941.0395 | 0 |  | #REF! | #REF!
| Programme monitoring | 15606.623 | 6000 | 2600 | 57.73 |  | 2.22% |  | 15606.623 | 6000 | 16262.3607 |  | #REF! | #REF!
| Capacity building for PM&E | 19000 | 611.2939 | 589.594 | 0 |  | 0% |  | 19000 | 1241.4917 | 19000 |  | #REF! | #REF!
| Local Office Costs Partner/Country Office | 37180.3279 | 15264.4056 | 14722.5468 | 14685.0602 |  | 99.75% |  | 37180.3279 | 17238.5901 | 36524.5902 |  | #REF! | #REF!
| Total country budget | 219000.0656 | 229000 | 210030.5009 | 170325.73 | 39704.7709 | 81.1% |  | 219000.0656 | 265000 | 219000.0656 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD | 30880 | 35094.4421 | 44761 | 28392.8 |  | 63.43% |  | 30880 | 47361.2 | 30880 |  | #REF! | #REF! | #VALUE!
| Total Budget | 249880.0656 | 264094.4421 | 254791.5009 | 198718.53 | 56072.9709 | 77.99% |  | 249880.0656 | 312361.2 | 249880.0656 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.5 | Ukraine
| Objective 1 (System) | To be decided | 0 | 0 | 0 |  | 0% | The slight overall programme underspending is due to COVID-related restrictions, which forced EECMD to conduct Democracy School sessions online (see section 2 of the narrative report). The PM&E budget could not be fully spent due to COVID-19 related restricitons (support was provided online). The capacity building activities for PM&E could not be implemented for the same reasons (support was provided online). The NIMD programme manager in charge of Ukraine left the organization in June 2020 and was not replaced (Ukraine is no longer part of NIMD's country programmes in 2021), creating on underspending on the NIMD staff costs line. | To be decided | 21176.4706 | To be decided
| Objective 2 (Actor) | 0 | 0 | 0 | 0 |  | 0% |  |  | 28235.2941
| Objective 3 (Culture) | 0 | 148000 | 181535 | 158583.3317 |  | 87.36% |  |  | 148235.2941
| Objective 4 (Gender equality & Inclusion) | 0 | 0 | 0 | 0 |  | 0% |  |  | 42352.9412
| Programme monitoring | 0 | 5000 | 0 | 0 |  | 0% |  |  | 5000
| Capacity building for PM&E | 0 | 19000 | 19000 | 3831.9437 |  | 20.17% |  |  | 19000
| Local Office Costs Partner/Country Office | 0 | 31000 | 33127.6 | 40584.7246 |  | 122.5% |  |  | 30000
| Total country budget | 169000 | 203000 | 233662.6 | 203000 | 30662.6 | 86.88% |  | 169000 | 294000 | 169000 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD | 23280 | 33693.3474 | 33693.3474 | 23136 |  | 68.67% |  | 23280 | 54593 | 23280 |  | #REF! | #REF! | #VALUE!
| Total budget | 192280 | 236693.3474 | 267355.9474 | 226136 | 41219.9474 | 84.58% |  | 192280 | 348593 | 192280 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.6 | Explatory countries
| Israel/Palestinian territories | [6 empty] | The overall underspending is due to the underspending on both Venezuela and MENA regional programme. See justification below.
| Jordan (1.6a) |  | 295059.72 | 305056 | 301606.92 |  | 98.87% |  |  | 306059 | 0 | 0 |  |  | #VALUE!
Kurdistan
| Lebanon | [8 empty] | 0 | 0 | 0 |  |  | #VALUE!
| MENA-region (1.6b) |  | 257545 | 154126.688 | 67396.28 |  | 43.73% |  |  | 379700 | 0 | 0 |  |  | #VALUE!
| Venezuela (1.6c) |  | 232834.4421 | 248350 | 134499.64 |  | 54.16%
| Total country budget | 365000 | 785439.1621 | 707532.688 | 503502.84 | 204029.848 | 71.16% |  | 365000 | 685759 | 400000 | 0 | #REF! | #REF! | #VALUE!
| Direct staff | 77440 | 123594.4421 | 127703.5579 | 128661.9 |  | 100.8% |  | 77440 | 98338.3 | 77440 |  | #REF! | #REF! | #VALUE!
| Total Budget | 442440 | 909033.6042 | 835236.2459 | 632164.74 | 203071.5059 | 75.69% |  | 442440 | 784097.3 | 477440 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.6a | Jordan
| Objective 1 (System) |  | 23667.3298 | 38185.6786 | 0 |  | 0% | Planned interventions on objective 1 and 4 could not be implemented all together, due to COVID-19 related restrictions. This underspending was used to make an additionnal investment on objective 3, which includes the series of radio debates included in the narrative report (section 2). The programme monitoring budget, which includes NIMD missions and travel costs, was drastically reduced in the revised annual plan but still could not be spent due to COVID-19 restrictions. |  | 29267.955 |  |  | #REF! | #REF!
| Objective 2 (Actor) |  | 188313.778 | 190653.5721 | 185751.952 |  | 97.43% |  |  | 178266.9463 |  |  | #REF! | #REF!
| Objective 3 (Culture) |  | 30398.4053 | 19092.8393 | 77199.2535 |  | 404.3% |  |  | 14124.7854 |  |  | #REF! | #REF!
| Objective 4 (Gender equality & Inclusion) |  | 6948.2069 | 9000.91 | 0 |  | 0% |  |  | 45199.3133 |  |  | #REF! | #REF!
| Programme monitoring |  | 6000 | 1800 | 618.08 |  | 34.34% |  |  | 6000 |  |  | #REF! | #REF!
| Capacity building for PM&E |  | 5280 | 14802 | 10700.8527 |  | 72.29% |  |  | 5000 |  |  | #REF! | #REF!
| Local Office Costs Partner/Country Office |  | 34452 | 31521 | 27336.7818 |  | 86.73% |  |  | 28200 |  |  | #REF! | #REF!
| Total country budget | 0 | 295059.72 | 305056 | 301606.92 | 3449.08 | 98.87% |  | 0 | 306059 | 0 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD |  | 39342.4421 | 48326 | 54741.4 |  | 113.3% |  |  | 50126.3 |  |  | #REF! | #REF! | #VALUE!
| Total budget | 0 | 334402.1621 | 353382 | 356348.32 | -2966.32 | 100.8% |  | 0 | 356185.3 | 0 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.6b | MENA-region
| Objective 1 (System) |  | 6350.1419 | 0 | 0 |  | 0% | The revised annual plan submitted in July 2020 still cattered for a couple of exchange visits, including a visit by Jordanians and Tunisians youth political party members to The Hague (objective 3), which could not be organized due to COVID-19 related restrictions. The regional training sessions (objective 2) were fully implemented online until the end of the year, leading to higher underspending than foreseen. The programme monitoring budget, which includes NIMD missions and travel costs, was drastically reduced in the revised annual plan but still could not be spent due to COVID-19 restrictions. The PM&E budget could not be spend for the same reasons. |  | 0 |  |  | #REF! | #REF!
| Objective 2 (Actor) |  | 166843.6288 | 92402.6258 | 49483.0229 |  | 53.55% |  |  | 370700 |  |  | #REF! | #REF!
| Objective 3 (Culture) |  | 75141.2293 | 57585.3742 | 17865.2571 |  | 31.02% |  |  | 0 |  |  | #REF! | #REF!
| Objective 4 (Gender equality & Inclusion) |  | 0 | 0 | 0 |  | 0% |  |  | 0 |  |  | #REF! | #REF!
| Programme monitoring |  | 8000 | 1000 | 48 |  | 4.8% |  |  | 8000 |  |  | #REF! | #REF!
| Capacity building for PM&E |  | 1210 | 2138.688 | 0 |  | 0% |  |  | 0 |  |  | #REF! | #REF!
| Local Office Costs Partner/Country Office |  | 0 | 1000 | 0 |  | 0% |  |  | 1000 |  |  | #REF! | #REF!
| Total country budget | 0 | 257545 | 154126.688 | 67396.28 | 86730.408 | 43.73% |  | 0 | 379700 | 0 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD |  | 52086.4421 | 47212 | 43797.5 |  | 92.77% |  |  | 48212 |  |  | #REF! | #REF! | #VALUE!
| Total budget | 0 | 309631.4421 | 201338.688 | 111193.78 | 90144.908 | 55.23% |  | 0 | 427912 | 0 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.6c | Venezuela
| Objective 1 (System) |  | 56798.0626 | 14278.824 | 30636.9471 |  | 214.6% | A number of activities foreseen under objective 2, such as a peer exchange visit for Members of Parliament, could not be implemented due to COVID-19 related restrictions. Some of these funds were used to produced 4 research papers, reported under objective 1. The underspending on objective 3 is due to higher COVID-19 related savings than foreseen, as the sessions of the Democracy Schools were mostly organized online. The programme monitoring budget, which includes NIMD missions and travel costs, could not be spent due to COVID-19 restrictions. The overspending on local office costs, although limited in absolute numbers, is linked to an extra-investment made by NIMD to ensure the sustainability of its programme and staff in Venezuela. |  |  |  |  | #REF! | #REF!
| Objective 2 (Actor) |  | 115100.7097 | 99647.9631 | 8164.8126 |  | 8.194% | [5 empty] | #REF! | #REF!
| Objective 3 (Culture) |  | 60935.6698 | 86766.641 | 47240.5905 |  | 54.45% | [5 empty] | #REF! | #REF!
| Objective 4 (Gender equality & Inclusion) |  | 0 | 36456.5719 | 34961.0315 |  | 95.9% | [5 empty] | #REF! | #REF!
| Programme monitoring |  | 0 | 4000 | 1956.26 |  | 48.91% | [5 empty] | #REF! | #REF!
| Capacity building for PM&E |  | 0 | 0 | 0 |  | 0% | [5 empty] | #REF! | #REF!
| Local Office Costs Partner/Country Office |  | 0 | 7200 | 11539.9984 |  | 160.3% | [5 empty] | #REF! | #REF!
| Total country budget | 0 | 232834.4421 | 248350 | 134499.64 | 113850.36 | 54.16% |  | 0 | 0 | 0 | 0 | #REF! | #REF! | #VALUE!
| Direct Staff Costs NIMD |  | 32165.5579 | 32165.5579 | 30123 |  | 93.65% | [5 empty] | #REF! | #REF! | #VALUE!
| Total budget | 0 | 265000 | 280515.5579 | 164622.64 | 115892.9179 | 58.69% |  | 0 | 0 | 0 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.7 | Enhanced knowledge and skills base for Fragile settings
| Expertise, skills and tools for Fragile and conflict affected settings | 280000 | 314116.4968 | 314116.4968 | 296659 |  | 94.44% | Only one peer learning exchange could be implemented in early 2020. Due to COVID-19 related restrictions, the other foreseen exchanges did not take place and all learning related activities were implemented online (see section 3.1 of the narrative report). | 280000 | 301000 | 280000 |  | #REF! | #REF! | #VALUE!
| Peer learning and exchange for Fragile and conflict affected settings | 160000 | 160000 | 160000 | 50676.06 |  | 31.67% |  | 160000 | 160000 | 160000 |  | #REF! | #REF! | #VALUE!
| Total budget | 440000 | 474116.4968 | 474116.4968 | 347335.06 | 126781.4368 | 73.26% |  | 440000 | 461000 | 440000 | 0 | #REF! | #REF! | #VALUE! | #REF!
1.8 | City Deals
| City Deals |  | 0 | 0 | 0 |  | 0% |  |  | 150000 |  |  | #REF! | #REF!
|  |  | 0 | 0 | 0 | 0 | 0% |  |  | 150000 |  |  | #REF! | #REF!
Total budget DfS country programmes |  | 1969185.3835 | 2388122.3167 | 2322747.6172 | 1902745.62 | 420001.9972 | 81.92% |  | 1969185.3835 | 2732219.3533 | 1958958.8866 | 0 | #REF! | #REF! | #VALUE! | #REF!
2. | Knowledge & Innovation
| Applied knowledge & Methodology development | 140000 | 146000 | 146000 | 134061.5 |  | 91.82% | The underspending on Peer learning & exchange is due to COVID-19 related restrictions, as the marjority of the learning happened online, triggering cost savings. This also partly explains the underspending on Piloting, although it should be noted that some of the pilots mentionned is section 3.2 of the narrative report were directly funded from country programme budgets. | 140000 | 135000 | 140000 |  | #REF! | #REF!
| Peer learning & exchange | 100000 | 100000 | 100000 | 34007.37 |  | 34.01% |  | 100000 | 100000 | 100000 |  | #REF! | #REF!
| Subtotal Knowledge | 240000 | 246000 | 246000 | 168068.87 | 77931.13 | 68.32% |  | 240000 | 235000 | 240000 | 0 | #REF! | #REF! | #VALUE!
| Mapping and convening |  | 65000 | 65000 | 58047.5 |  | 89.3% |  |  | 60000
| Piloting |  | 100000 | 100000 | 10770.25 |  | 10.77% |  |  | 100000
| Subtotal Innovation | 160000 | 165000 | 165000 | 68817.75 | 96182.25 | 41.71% |  | 160000 | 160000 | 150000 | 0 | #REF! | #REF! | #VALUE!
Total budget Knowledge & Innovation |  | 400000 | 411000 | 411000 | 236886.62 | 174113.38 | 57.64% |  | 400000 | 395000 | 390000 | 0 | #REF! | #REF! | #VALUE! | #REF!
II - | Organisational Development
3. | Fundraising & Positioning
| Internal Fundraising capacity | 80000 | 133000 | 133000 | 136701 |  | 102.8% | The overspending is due to the implementation of additionnal Positioning interventions around the COVID-19 crisis and its effects, as described in section 4.1 of the narrative report. | 80000 | 80000 | 80000 |  | #REF! | #REF!
| Positioning | 70000 | 70000 | 70000 | 89852.45 |  | 128.4% |  | 70000 | 70000 | 70000 |  | #REF! | #REF!
| Total budget | 150000 | 203000 | 203000 | 226553.45 | -23553.45 | 111.6% |  | 150000 | 150000 | 150000 | 0 | #REF! | #REF! | #VALUE! | #REF!
4. | Planning, Monitoring & Evaluation
| Internal PME capacity | 40000 | 50000 | 50000 | 37626.55 |  | 75.25% | The costs foreseen to integrate IATI reporting into NIMD's new Project Management System were lower than foreseen | 40000 | 50000 | 40000 |  | #REF! | #REF!
| Final programme evaluation | 180000 | 75000 | 75000 | 81917 |  | 109.2% |  | 180000 | 60000 |  | 60000 | #REF! | #REF!
| Capacity building country PME | 100000 | 119000 | 119000 | 122724 |  | 103.1% |  | 100000 | 138000 | 100000 |  | #REF! | #REF!
| IATI implementation | 25000 | 25000 | 25000 | 10069.4 |  | 40.28% |  | 25000 | 93000 | 25000 |  | #REF! | #REF!
| Total budget | 345000 | 269000 | 269000 | 252336.95 | 16663.05 | 93.81% |  | 345000 | 341000 | 165000 | 60000 | #REF! | #REF! | #VALUE! | #REF!
5. | Coordination
| Internal Coordination capacity | 0 | 25000 | 25000 | 29293 |  | 117.2% | The staff costs on programme coordination were slightly higher than foreseen. | 0 | 21000 | 0 |  | #REF! | #REF!
| Total budget | 0 | 25000 | 25000 | 29293 |  | 117.2% |  | 0 | 21000 | 0 |  | #REF! | #REF! | #VALUE!
Total budget Institutional Development |  | 495000 | 497000 | 497000 | 508183.4 | -11183.4 | 102.3% |  | 495000 | 512000 | 315000 | 60000 | #REF! | #REF! | #VALUE! | #REF!
III - | Programme overhead
| Overhead & office running cost (12,78%) | 340000 | 421880.5919 | 432996.7767 | 348298.9811 |  | 80.44% | The sustainability budget, which was added to the revised annual plan, was partly used to cover the staff hours spent in Q1 of 2021 to work on the final reporting of the programme. This was approved by the MFA in April 2021. | 340000 | 417493.6553 | 340000 |  | #REF! | #REF! | #VALUE!
| Sustainbility budget |  | 0 | 475523.4945 | 57528.5 |  | 12.1%
| Audit | 20000 | 20000 | 20000 | 20000 |  | 100% |  | 20000 | 20000 | 20000 |  | #REF! | #REF! | 0
|  | 360000 | 441880.5919 | 928520.2711 | 425827.4811 | 502692.7901 | 45.86% |  | 360000 | 437493.6553 | 360000 | 0 | #REF! | #REF! | #VALUE! | #REF!
Total DfS Budget |  | 3224185.3835 | 3738002.9086 | 4159267.8883 | 3073643.1211 | 1085624.7672 | 73.9% |  | 3224185.3835 | 4076713.0086 | 3023958.8866 | 60000 | #REF! | #REF! | #VALUE! | #REF!
[5 empty] | 2725344.14 | [7 empty] | #REF! | #REF!
[13 empty] | #REF! | #REF!
[9 empty] | TRUE | TRUE | TRUE |  | #REF! | #REF!
-852527.6252
#REF!
#REF!

## Financial Report DfS 2016-2020
Financial Report 2016-2020 DfS NIMD
|  | Original Budget | Actuals | Deviation |  | Original Budget | Updated Budget | Actuals | Deviation |  | Original Budget | Updated Budget | Actuals | Deviation |  | Original Budget | Updated Budget | Actuals | Deviation | Original Budget | Updated Budget | Updated Budget | Actuals | Deviation | Original Budget |  | Actuals | Deviation
|  | 2016 |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  | 2020 |  |  |  |  | 2016-2020
I - | Programmes
1. | Dialogue for Stability country programmes
1.1 | Burundi
| Objective 1 (System) | 23840.3691 | 5783.75 |  |  | 34030.1611 | 88732.5776 | 44424.5364 |  |  | 43803.5237 | 60936.8844 | 29303.0195 |  |  | 24677.4542 | 59777.2079 | 6723.4058 |  | 25947.3472 | 55006.8327 | 53325.6126 | 16966.6211 |  | 152298.8553 | 139560.3244 | 103201.3328
| Objective 2 (Actor) | 0 | 5783.75 |  |  | 23945.6252 | 88976.5922 | 0 |  |  | 67349.1955 | 88674.7411 | 16212.5742 |  |  | 104069.492 | 52284.6902 | 16587.5274 |  | 72976.395 | 0 | 0 | 0 |  | 268340.7077 | 38583.8517 | 38583.8517
| Objective 3 (Culture) | 70981.4145 | 12114.5 |  |  | 67398.4195 | 12323.9691 | 0 |  |  | 47933.3195 | 31585.5295 | 167325.8757 |  |  | 51594.78 | 151107.6184 | 198813.129 |  | 36166.043 | 54292.5836 | 52635.533 | 140294.6944 |  | 274073.9765 | 430889.0377 | 518548.1991
| Objective 4 (Gender equality & Inclusion) | 19833.4165 | 29214 |  |  | 19822.3842 | 55457.861 | 0 |  |  | 17735.1663 | 18786.845 | 1326.3049 |  |  | 476.7657 | 18394.4836 | 53694.6529 |  | 502.2098 | 54292.5836 | 52630.8544 | 11869.9961 |  | 58369.9424 | 136865.8122 | 96104.9539
| Programme monitoring | 16937.195 | 1627 |  |  | 16937.195 | 13049 | 0 |  |  | 16937.195 | 16937 | 20317.57 |  |  | 16937.195 | 16937 | 9084.52 |  | 16937.195 | 16937 | 4000 | 206.24 |  | 84685.975 | 35029.09 | 31235.33
| Capacity building for PM&E | 19000 | 0 |  |  | 19000 | 10000 | 20572.6754 |  |  | 19000 | 19000 | 12373.1182 |  |  | 19000 | 19000 | 0 |  | 19000 | 19000 | 19000 | 0 |  | 95000 | 51945.7936 | 32945.7936
| Local Office Costs Partner/Country Office | 42749.631 | 127158.03 |  |  | 42749.631 | 19588 | 30191.3782 |  |  | 42749.631 | 19587 | 24245.5874 |  |  | 42749.631 | 20000 | 24679.3149 |  | 42749.631 | 15000 | 20000 | 20508.9284 |  | 213748.155 | 226274.3104 | 226783.2388
| Total country budget | 193342.026 | 181681.03 | 11660.996 |  | 223883.416 | 288128 | 95188.59 | 128694.826 |  | 255508.031 | 255508 | 271104.05 | -15596.05 |  | 259505.3179 | 337501 | 309582.55 | 27918.45 | 214278.821 | 214529 | 201592 | 189846.48 |  | 1146517.6119 | 1059148.22 | 1047402.7
| Direct Staff Costs NIMD | 46080 | 46080 |  |  | 46080 | 46080 | 50291 |  |  | 46080 | 46080 | 64718 |  |  | 46080 | 72459.8 | 54332 |  | 46080 | 59181.3474 | 59181.3474 | 66798 |  | 230400 | 274602.3474 | 282219
| Total Budget | 239422.026 | 227761.03 | 11660.996 |  | 269963.416 | 334208 | 145479.59 | 124483.826 |  | 301588.031 | 301588 | 335822.05 | -34234.05 |  | 305585.3179 | 409960.8 | 363914.55 | 46046.25 | 260358.821 | 273710.3474 | 260773.3474 | 256644.48 | -13351.5264 | 1376917.6119 | 1333750.5674 | 1329621.7 | 4128.8674 | 0.2999%
1.2 | Colombia
| Objective 1 (System) | 36728.4727 | 37108.75 |  |  | 33363.2382 | 35650.7262 | 16098.98 |  |  | 31786.2245 | 44538.2224 | 35109.1359 |  |  | 31786.2245 | 32487.3901 | 32489.1023 |  | 31786.2245 | 39962.3265 | 39962.3265 | 51325.8622 |  | 165450.3844 | 160768.2947 | 172131.8303
| Objective 2 (Actor) | 36735.1255 | 33262.75 |  |  | 41269.4345 | 51247.919 | 15662.4248 |  |  | 39318.7107 | 32773.3844 | 29656.0289 |  |  | 39318.7107 | 43497.7608 | 36149.4529 |  | 39318.7107 | 25899.7876 | 25899.7876 | 43175.292 |  | 195960.6922 | 140630.4442 | 157905.9486
| Objective 3 (Culture) | 39712.0309 | 46846.75 |  |  | 61457.8964 | 66845.1117 | 48382.9214 |  |  | 58552.9042 | 54369.3728 | 33340.7469 |  |  | 58552.9042 | 97869.9618 | 60217.2448 |  | 58552.9042 | 30841.5927 | 30841.5927 | 20896.3023 |  | 276828.64 | 219629.2556 | 209683.9653
| Objective 4 (Gender equality & Inclusion) | 20851.6436 | 24514.75 |  |  | 18436.7036 | 17825.3631 | 5916.5854 |  |  | 17565.2374 | 32773.4104 | 31178.9401 |  |  | 17565.2374 | 38060.5407 | 42041.2762 |  | 17565.2374 | 28150.4132 | 28150.4132 | 42261.7571 |  | 91984.0596 | 131801.9648 | 145913.3088
| Programme monitoring | 19200 | 13864.97 |  |  | 19200 | 10000 | 13317.065 |  |  | 18292.4543 | 19200 | 7732.84 |  |  | 18292.4543 | 7500 | 610.6 |  | 18292.4543 | 7500 | 7500 | 1147.69 |  | 93277.3629 | 43025.475 | 36673.165
| Capacity building for PM&E | 19000 | 0 |  |  | 19000 | 28000 | 30183.7998 |  |  | 18101.9079 | 24838.71 | 16506.5206 |  |  | 18101.9079 | 19000 | 14919.6316 |  | 18101.9079 | 10000 | 10000 | 6696.9697 |  | 92305.7237 | 71609.952 | 68306.9217
| Local Office Costs Partner/Country Office | 37138 | 26138 |  |  | 37138 | 20295.8842 | 131989.7838 |  |  | 35382.5609 | 30432.26 | 16214.9378 |  |  | 35382.5609 | 24900 | 24959.7622 |  | 35382.5609 | 47600.0009 | 47600.0009 | 41672.9366 |  | 180423.6826 | 246902.4846 | 240975.4204
| Total country budget | 209365.2727 | 181735.97 | 27629.3027 |  | 229865.2727 | 229865.0042 | 261551.56 | -31686.2873 |  | 219000 | 238925.36 | 169739.15 | 69186.21 |  | 219000 | 263315.6533 | 211387.07 | 51928.5833 | 219000 | 189954.1209 | 189954.1209 | 207176.81 |  | 1096230.5455 | 1014367.8709 | 1031590.56
| Direct Staff Costs NIMD | 38720 | 38720 |  |  | 38720 | 39881.6 | 49920.5 |  |  | 38720 | 38720 | 36627 |  |  | 38720 | 52891.4 | 31800 |  | 38720 | 40519.9579 | 40519.9579 | 34570 |  | 193600 | 197587.4579 | 191637.5
| Total Budget | 248085.2727 | 220455.97 | 27629.3027 |  | 268585.2727 | 269746.6042 | 311472.06 | -42886.7873 |  | 257720 | 277645.36 | 206366.15 | 71279.21 |  | 257720 | 316207.0533 | 243187.07 | 73019.9833 | 257720 | 230474.0788 | 230474.0788 | 241746.81 | 27245.9212 | 1289830.5455 | 1211955.3288 | 1223228.06 | -11272.7312 | -0.874%
1.3 | South Sudan
| conference | 20000 | 0 | [13 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0
| peer exchange | 15000 | 0 | [13 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0
| Programme monitoring | 15000 | 0 | [13 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0
| Capacity building for PM&E | 8000 | 0 | [13 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0
| Total country budget | 58000 | 0 | 58000 |  | 58000 | 0 | 0 | 58000 |  | 58000 | 0 |  | 0 |  | 58000 | 0 |  | 0 | 58000 | 0 | 0 | 0 |  | 290000 | 0 | 0
| Direct Staff Costs NIMD | 23280 | 12000 |  |  | 23280 |  |  |  |  | 23280 |  |  |  |  | 23280 | 0 |  |  | 23280 | 0 | 0 | 0 |  | 116400 | 12000 | 12000
| Total Budget | 81280 | 12000 | 69280 |  | 81280 | 0 | 0 | 81280 |  | 81280 | 0 |  | 0 |  | 81280 | 0 | 0 | 0 | 81280 | 0 | 0 | 0 | 81280 | 406400 | 12000 | 12000 | 0 | 0%
1.4 | Tunisia
| Objective 1 (System) | 23410.3322 | 34399.6667 |  |  | 24823.3967 | 16498.4448 | 6476.9332 |  |  | 24823.3967 | 74204.7141 | 22708.2509 |  |  | 24823.3967 | 93676.4296 | 76588.3022 |  | 24823.3967 | 89063.9936 | 80123.9847 | 67354.2305 |  | 122703.9191 | 220297.1376 | 207527.3834
| Objective 2 (Actor) | 82873.7085 | 97819.6667 |  |  | 79888.3672 | 131100.9946 | 56683.8933 |  |  | 79888.3672 | 118941.7643 | 156936.3445 |  |  | 79888.3672 | 124219.0201 | 95366.2124 |  | 79888.3672 | 101378.3363 | 96020.0229 | 79605.5982 |  | 402427.1773 | 502826.1398 | 486411.7151
| Objective 3 (Culture) | 42529.5186 | 18866.6667 |  |  | 42501.3508 | 13286.8818 | 6057.7145 |  |  | 42501.3508 | 13405.3881 | 12086.2752 |  |  | 42501.3508 | 10683.429 | 3135.3859 |  | 42501.3508 | 9159.0267 | 8593.5446 | 1666.6661 |  | 212534.9219 | 48739.5868 | 41812.7083
| Objective 4 (Gender equality & Inclusion) | 0 | 0 |  |  | 0 | 7010.3382 | 3190.5205 |  |  | 0 | 11260.6379 | 10688.3916 |  |  | 0 | 11941.0395 | 12305.502 |  | 0 | 7522.9439 | 7380.808 | 6956.4449 |  | 0 | 33565.2221 | 33140.859
| Programme monitoring | 13423.2542 | 12081 |  |  | 15606.623 | 14800 | 1511.0532 |  |  | 14557.4426 | 14557.4426 | 2790.87 |  |  | 15606.623 | 6000 | 1194.8 |  | 16262.3607 | 6000 | 2600 | 57.73 |  | 75456.3034 | 20177.7232 | 17635.4532
| Capacity building for PM&E | 19000 | 0 |  |  | 19000 | 2700 | 2986.4975 |  |  | 19000 | 8968.695 | 10506.7345 |  |  | 19000 | 1241.4917 | 1243.0726 |  | 19000 | 611.2939 | 589.594 | 0 |  | 95000 | 15325.8986 | 14736.3045
| Local Office Costs Partner/Country Office | 37762.7119 | 7234 |  |  | 37180.3279 | 11449.5781 | 59718.1478 |  |  | 38229.5082 | 14042.5639 | 14992.8233 |  |  | 37180.3279 | 17238.5901 | 14383.6151 |  | 36524.5902 | 15264.4056 | 14722.5468 | 14685.0602 |  | 186877.466 | 111051.133 | 111013.6464
| Total country budget | 218999.5254 | 170401 | 48598.5254 |  | 219000.0656 | 196846.2373 | 136624.76 | 82375.3056 |  | 219000.0656 | 255381.206 | 230709.69 | 24671.516 |  | 219000.0656 | 265000 | 204216.89 | 60783.11 | 219000.0656 | 229000 | 210030.5009 | 170325.73 |  | 1094999.7877 | 951982.8409 | 912278.07
| Direct Staff Costs NIMD | 30880 | 30880 |  |  | 30880 | 31806.4 | 34852.5 |  |  | 30880 | 30880 | 60264 |  |  | 30880 | 47361.2 | 36031.2 |  | 30880 | 35094.4421 | 44761 | 28392.8 |  | 154400 | 206788.7 | 190420.5
| Total Budget | 249879.5254 | 201281 | 48598.5254 |  | 249880.0656 | 228652.6373 | 171477.26 | 78402.8056 |  | 249880.0656 | 286261.206 | 290973.69 | -4712.484 |  | 249880.0656 | 312361.2 | 240248.09 | 72113.11 | 249880.0656 | 264094.4421 | 254791.5009 | 198718.53 | -14214.3765 | 1249399.7877 | 1158771.5409 | 1102698.57 | 56072.9709 | 4.488%
1.5 | Ukraine
| Objective 1 (System) | 24232.834 | 36540.3333 |  |  | 24221.0674 | 29881.2149 | 26319.0437 |  |  | 24221.0674 | 19098.5 | 31375.7221 |  |  | 24221.0674 | 21176.4706 | 5900.6504 |  | 24221.0674 | 0 | 0 | 0 |  | 121117.1037 | 100135.7496 | 100135.7496
| Objective 2 (Actor) | 17096.7512 | 43095.3333 |  |  | 17088.4496 | 23904.9719 | 10700.5267 |  |  | 17088.4496 | 15915.4167 | 9337.3952 |  |  | 17088.4496 | 28235.2941 | 10300.8985 |  | 17088.4496 | 0 | 0 | 0 |  | 85450.5496 | 73434.1537 | 73434.1537
| Objective 3 (Culture) | 29735.5021 | 25353.3333 |  |  | 29721.0637 | 49802.0248 | 54491.6981 |  |  | 29721.0637 | 105041.75 | 106706.5641 |  |  | 29721.0637 | 148235.2941 | 87724.7351 |  | 29721.0637 | 148000 | 181535 | 158583.3317 |  | 148619.7569 | 455811.3307 | 432859.6624
| Objective 4 (Gender equality & Inclusion) | 12489.5127 | 0 |  |  | 12483.4483 | 16932.6884 | 21025.4719 |  |  | 12483.4483 | 12732.3333 | 15086.5092 |  |  | 12483.4483 | 42352.9412 | 132323.9887 |  | 12483.4483 | 0 | 0 | 0 |  | 62423.3057 | 168435.9698 | 168435.9698
| Programme monitoring | 22000 | 8723.1 |  |  | 21989.3176 | 8000 | 0 |  |  | 21989.3176 | 8000 | 3368.81 |  |  | 21989.3176 | 5000 | 1256.21 |  | 21989.3176 | 5000 | 0 | 0 |  | 109957.2705 | 13348.12 | 13348.12
| Capacity building for PM&E | 19000 | 0 |  |  | 18990.7743 | 19000 | 0 |  |  | 18990.7743 | 19000 | 0 |  |  | 18990.7743 | 19000 | 453.6419 |  | 18990.7743 | 19000 | 19000 | 3831.9437 |  | 94963.0972 | 19453.6419 | 4285.5856
| Local Office Costs Partner/Country Office | 44527.5 | 43422 |  |  | 44505.8791 | 21596 | 78934.8595 |  |  | 44505.8791 | 29212 | 36797.4893 |  |  | 44505.8791 | 30000 | 44485.3654 |  | 44505.8791 | 31000 | 33127.6 | 40584.7246 |  | 222551.0164 | 236767.3143 | 244224.4388
| Total country budget | 169082.1 | 157134.1 | 0 |  | 169000 | 169116.9 | 191471.6 | -22471.6 |  | 169000 | 209000 | 202672.49 | 6327.51 |  | 169000 | 294000 | 282445.49 | 11554.51 | 169000 | 203000 | 233662.6 | 203000 |  | 845082.1 | 1067386.28 | 1036723.68
| Direct Staff Costs NIMD | 23280 | 23280 |  |  | 23280 | 23978.4 | 25939 |  |  | 23280 | 23280 | 29212 |  |  | 23280 | 54593 | 32672 |  | 23280 | 33693.3474 | 33693.3474 | 23136 |  | 116400 | 144796.3474 | 134239
| Total budget | 192362.1 | 180414.1 | 11948 |  | 192280 | 193095.3 | 217410.6 | -25130.6 |  | 192280 | 232280 | 231884.49 | 395.51 |  | 192280 | 348593 | 315117.49 | 33475.51 | 192280 | 236693.3474 | 267355.9474 | 226136 | -44413.3474 | 961482.1 | 1212182.6274 | 1170962.68 | 41219.9474 | 4.287%
1.6 | Exploratory countries
| Israel/Palestinian territories | 50000 | 9097.05 | [16 empty] | 0 | 0 | 0 | 0 |  |  | 9097.05 | 9097.05
| Jordan (1.6a) | 50000 | 45132 |  |  |  | 180350 | 175660.45 |  |  |  | 205290.5 | 33848.97 |  |  |  | 306059 | 272665.66 |  | 0 | 295059.72 | 305056 | 301606.92 |  |  | 832363.08 | 828914
| Kurdistan | 50000 | 6508.01 | [16 empty] | 0 | 0 | 0 | 0 |  |  | 6508.01 | 6508.01
| Venezuela (1.6d) | 0 | 0 | [16 empty] | 0 | 232834.4421 | 0 | 0 |  |  | 0 | 0
| Lebanon (1.6c) | 50000 | 21730.21 |  |  |  | 180350 | 7713.41 |  |  |  | 142950 | -5.6843e-14 |  |  |  | 0 | 209894.03 |  | 0 | 0 | 154126.688 | 67396.28 |  |  | 393464.338 | 306733.93
| MENA-region (1.6b) | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 379700 | 7735.17 |  | 0 | 257545 | 248350 | 134499.64 |  |  | 256085.17 | 142234.81
| Total country budget | 200000 | 82467.27 | 117532.73 |  | 245000 | 360700 | 183373.86 | 0 |  | 305000 | 348240.5 | 33848.97 | 314391.53 |  | 365000 | 685759 | 490294.86 | 195464.14 | 400000 | 785439.1621 | 707532.688 | 503502.84 |  | 1515000 | 1497517.648 | 1293487.8
| Direct staff | 77440 | 157440 |  |  | 77440 | 160000 | 60971.5 |  |  | 77440 | 128000 | 57973 |  |  | 77440 | 98338.3 | 111032.7 |  | 77440 | 123594.4421 | 127703.5579 | 128661.9 |  | 387200 | 515120.7579 | 516079.1
| Total Budget | 277440 | 239907.27 | 37532.73 |  | 322440 | 520700 | 244345.36 | 0 |  | 382440 | 476240.5 | 91821.97 | 384418.53 |  | 442440 | 784097.3 | 601327.56 | 182769.74 | 477440 | 909033.6042 | 835236.2459 | 632164.74 | -431593.6042 | 1902200 | 2012638.4059 | 1809566.9 | 203071.5059 | 10.68%
1.6a | Jordan
| Objective 1 (System) | [5 empty] | 23500.184 | 0 |  |  |  | 82880.525 | 7855.6499 |  |  |  | 29267.955 | 20296.1216 |  |  | 23667.3298 | 38185.6786 | 0 |  | 0 | 66337.4502 | 28151.7715
| Objective 2 (Actor) | [5 empty] | 125028.8344 | 107904.6519 |  |  |  | 82452.125 | 7815.0449 |  |  |  | 178266.9463 | 181293.8242 |  |  | 188313.778 | 190653.5721 | 185751.952 |  | 0 | 487667.093 | 482765.473
| Objective 3 (Culture) | [5 empty] | 11520.9816 | 0 |  |  |  | 30957.85 | 2934.2723 |  |  |  | 14124.7854 | 22842.4145 |  |  | 30398.4053 | 19092.8393 | 77199.2535 |  | 0 | 44869.5262 | 102975.9404
| Objective 4 (Gender equality & Inclusion) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 45199.3133 | 0 |  |  | 6948.2069 | 9000.91 | 0 |  | 0 | 9000.91 | 0
| Programme monitoring | [5 empty] | 8000 | 18294.0915 |  |  |  | 9000 | 14975.14 |  |  |  | 6000 | 6238.32 |  |  | 6000 | 1800 | 618.08 |  | 0 | 41307.5515 | 40125.6315
| Capacity building for PM&E | [5 empty] | 6000 | 0 |  |  |  | 0 | 0 |  |  |  | 5000 | 0 |  |  | 5280 | 14802 | 10700.8527 |  | 0 | 14802 | 10700.8527
| Local Office Costs Partner/Country Office | [5 empty] | 6300 | 49461.7066 |  |  |  | 0 | 268.8628 |  |  |  | 28200 | 41994.9797 |  |  | 34452 | 31521 | 27336.7818 |  | 0 | 123246.5491 | 119062.3309
| Total country budget | 0 | 0 | 0 |  | 0 | 180350 | 175660.45 | -175660.45 |  | 0 | 205290.5 | 33848.97 | 171441.53 |  | 0 | 306059 | 272665.66 | 33393.34 | 0 | 295059.72 | 305056 | 301606.92 |  | 0 | 787231.08 | 783782
| Direct Staff Costs NIMD | [5 empty] | 80000 | 48754.5 |  |  |  | 60000 | 57973 |  |  |  | 50126.3 | 43793.6 |  |  | 39342.4421 | 48326 | 54741.4 |  | 0 | 198847.1 | 205262.5
| Total budget | 0 | 0 | 0 |  | 0 | 260350 | 224414.95 | -224414.95 |  | 0 | 265290.5 | 91821.97 | 173468.53 |  | 0 | 356185.3 | 316459.26 | 39726.04 | 0 | 334402.1621 | 353382 | 356348.32 | -334402.1621 | 0 | 986078.18 | 989044.5
1.6b | MENA-region
| Objective 1 (System) | [11 empty] | 0 |  |  |  | 0 | 82450.039 |  |  | 6350.1419 | 0 | 0 |  | 0 | 82450.039 | 82450.039
| Objective 2 (Actor) | [11 empty] | 0 |  |  |  | 370700 | 102665.1291 |  |  | 166843.6288 | 92402.6258 | 49483.0229 |  | 0 | 195067.7548 | 152148.152
| Objective 3 (Culture) | [11 empty] | 0 |  |  |  | 0 | 3375.3547 |  |  | 75141.2293 | 57585.3742 | 17865.2571 |  | 0 | 60960.7289 | 21240.6118
| Objective 4 (Gender equality & Inclusion) | [11 empty] | 0 |  |  |  | 0 | 13247.3118 |  |  | 0 | 0 | 0 |  | 0 | 13247.3118 | 13247.3118
| Programme monitoring | [11 empty] | 0 |  |  |  | 8000 | 6015.64 |  |  | 8000 | 1000 | 48 |  | 0 | 7015.64 | 6063.64
| Capacity building for PM&E | [11 empty] | 0 |  |  |  | 0 | 1338.2119 |  |  | 1210 | 2138.688 | 0 |  | 0 | 3476.8999 | 1338.2119
| Local Office Costs Partner/Country Office | [11 empty] | 0 |  |  |  | 1000 | 802.3436 |  |  | 0 | 1000 | 0 |  | 0 | 1802.3436 | 802.3436
| Total country budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 379700 | 209894.03 | 169805.97 | 0 | 257545 | 154126.688 | 67396.28 |  | 0 | 364020.718 | 277290.31
| Direct Staff Costs NIMD | [11 empty] | 0 |  |  |  | 48212 | 49179.1 |  |  | 52086.4421 | 47212 | 43797.5 |  | 0 | 96391.1 | 92976.6
| Total budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 427912 | 259073.13 | 168838.87 | 0 | 309631.4421 | 201338.688 | 111193.78 | -309631.4421 | 0 | 460411.818 | 370266.91
1.6c | Lebanon
| Objective 1 (System) | [5 empty] | 23500.184 | 0 |  |  |  | 20232.7469 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Objective 2 (Actor) | [5 empty] | 125028.8344 | 0 |  |  |  | 45086.9012 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Objective 3 (Culture) | [5 empty] | 11520.9816 | 0 |  |  |  | 67630.3518 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Objective 4 (Gender equality & Inclusion) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Programme monitoring | [5 empty] | 8000 | 7713.41 |  |  |  | 5000 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 7713.41 | 7713.41
| Capacity building for PM&E | [5 empty] | 6000 | 0 |  |  |  | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Local Office Costs Partner/Country Office | [5 empty] | 6300 | 0 |  |  |  | 5000 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 | 0
| Total country budget | 0 | 0 | 0 |  | 0 | 180350 | 7713.41 | -7713.41 |  | 0 | 142950 | -5.6843e-14 | 142950 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 7713.41 | 7713.41
| Direct Staff Costs NIMD | [5 empty] | 80000 | 12217 |  |  |  | 68000 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 12217 | 12217
| Total budget | 0 | 0 | 0 |  | 0 | 260350 | 19930.41 | -19930.41 |  | 0 | 210950 | -5.6843e-14 | 210950 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 19930.41 | 19930.41
1.6d | Venezuela
| Objective 1 (System) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 56798.0626 | 14278.824 | 30636.9471 |  | 0 | 14278.824 | 30636.9471
| Objective 2 (Actor) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 115100.7097 | 99647.9631 | 8164.8126 |  | 0 | 99647.9631 | 8164.8126
| Objective 3 (Culture) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 60935.6698 | 86766.641 | 47240.5905 |  | 0 | 86766.641 | 47240.5905
| Objective 4 (Gender equality & Inclusion) | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 0 | 36456.5719 | 34961.0315 |  | 0 | 36456.5719 | 34961.0315
| Programme monitoring | [5 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 7735.17 |  |  | 0 | 4000 | 1956.26 |  | 0 | 11735.17 | 9691.43
| Capacity building for PM&E | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
| Local Office Costs Partner/Country Office | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | [7 empty] | 0 | 7200 | 11539.9984 |  | 0 | 7200 | 11539.9984
| Total country budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | -5.6843e-14 | 5.6843e-14 |  | 0 | 0 | 7735.17 | -7735.17 | 0 | 232834.4421 | 248350 | 134499.64 |  | 0 | 256085.17 | 142234.81
| Direct Staff Costs NIMD | [5 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  |  | 18060 |  |  | 32165.5579 | 32165.5579 | 30123 |  | 0 | 50225.5579 | 48183
| Total budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | -5.6843e-14 | 5.6843e-14 |  | 0 | 0 | 25795.17 | -25795.17 | 0 | 265000 | 280515.5579 | 164622.64 | -265000 | 0 | 306310.7279 | 190417.81
1.7 | Enhanced knowledge and skills base for Fragile settings
| Expertise, skills and tools for Fragile and conflict affected settings | 280000 | 292464 |  |  | 280000 | 354800 | 305468.4701 |  |  | 280000 | 428269.6 | 388876.4082 |  |  | 280000 | 301000 | 225855.5 |  | 280000 | 314116.4968 | 314116.4968 | 296659 |  | 1400000 | 1526780.8751 | 1509323.3783
| Peer learning and exchange for Fragile and conflict affected settings | 160000 | 0 |  |  | 160000 | 211200 | 181834.6699 |  |  | 160000 | 80000 | 72641.4218 |  |  | 160000 | 160000 | 104380.57 |  | 160000 | 160000 | 160000 | 50676.06 |  | 800000 | 518856.6617 | 409532.7217
| Total budget | 440000 | 292464 | 147536 |  | 440000 | 566000 | 487303.14 | -47303.14 |  | 440000 | 508269.6 | 461517.83 | 46751.77 |  | 440000 | 461000 | 330236.07 | 130763.93 | 440000 | 474116.4968 | 474116.4968 | 347335.06 | -34116.4968 | 2200000 | 2045637.5368 | 1918856.1 | 126781.4368 | 5.763%
1.8 | City Deals
| City Deals | [11 empty] | 11338 |  |  |  | 150000 | 24258.78 |  |  | 0 | 0 | 0 |  | 0 | 35596.78 | 35596.78
[13 empty] | 11338 | -11338 |  |  | 150000 | 24258.78 | 125741.22 | 0 | 0 | 0 | 0 | 0 | 0 | 35596.78 | 35596.78 | 0
Total budget DfS country programmes |  | 1728468.9242 | 1374283.37 | 354185.5542 |  | 1824428.7543 | 2112402.5416 | 1577488.01 | 246940.7443 |  | 1905188.0966 | 2082284.666 | 1629724.18 | 452560.486 |  | 1969185.3835 | 2782219.3533 | 2118289.61 | 663929.7433 | 1958958.8866 | 2388122.3167 | 2322747.6172 | 1902745.62 | -429163.4301 | 9386230.0451 | 9022532.7872 | 8602530.79 | 420001.9972 | 4.475%
2. | Knowledge & Innovation
| Applied knowledge & Methodology development | 140000 | 179816 |  |  | 140000 | 122080 | 159677.1079 |  |  | 140000 | 185817.5 | 191691.336 |  |  | 140000 | 135000 | 112297.5 |  | 140000 | 146000 | 146000 | 134061.5 |  | 700000 | 789481.9439 | 777543.4439
| Peer learning & exchange | 100000 |  |  |  | 100000 | 101200 | 132366.6721 |  |  | 100000 | 95000 | 98003.024 |  |  | 100000 | 100000 | 120721.75 |  | 100000 | 100000 | 100000 | 34007.37 |  | 500000 | 451091.4461 | 385098.8161
| Subtotal Knowledge | 240000 | 179816 | 60184 |  | 240000 | 223280 | 292043.78 | -52043.78 |  | 240000 | 280817.5 | 289694.36 | -8876.86 |  | 240000 | 235000 | 233019.25 | 1980.75 | 240000 | 246000 | 246000 | 168068.87 | -6000 | 1200000 | 1240573.39 | 1162642.26 | 77931.13 | 6.494%
| Mapping and convening | 85000 | 81241.57 |  |  |  | 180000 | 153972.03 |  |  |  | 195859.75 | 191078.25 |  |  |  | 60000 | 74928.5 |  |  | 65000 | 65000 | 58047.5 |  |  | 566220.35 | 559267.85
| Piloting | 115000 | [10 empty] | 0 |  |  |  | 100000 | 77948.16 |  |  | 100000 | 250000 | 10770.25 |  |  | 327948.16 | 88718.41
| Subtotal Innovation | 200000 | 81241.57 | 118758.43 |  | 180000 | 180000 | 153972.03 | 26027.97 |  | 170000 | 195859.75 | 191078.25 | 4781.5 |  | 160000 | 160000 | 152876.66 | 7123.34 | 150000 | 165000 | 315000 | 68817.75 | -15000 | 860000 | 894168.51 | 647986.26 | 246182.25 | 28.63%
Total budget Knowledge & Innovation |  | 440000 | 261057.57 | 178942.43 |  | 420000 | 403280 | 446015.81 | -26015.81 |  | 410000 | 476677.25 | 480772.61 | -4095.36 |  | 400000 | 395000 | 385895.91 | 9104.09 | 390000 | 411000 | 561000 | 236886.62 | -21000 | 2060000 | 2134741.9 | 1810628.52 | 324113.38 | 15.73%
II - | Organisational Development
3. | Fundraising & Positioning
| Internal Fundraising capacity | 80000 | 80000 |  |  | 80000 | 82400 | 95645.5517 |  |  | 80000 | 80000 | 78986.5694 |  |  | 80000 | 80000 | 58078 |  | 80000 | 133000 | 133000 | 136701 |  | 400000 | 445710.1211 | 449411.1211
| Positioning | 70000 | 52260 |  |  | 70000 | 120000 | 139289.6383 |  |  | 70000 | 90000 | 88859.8906 |  |  | 70000 | 70000 | 97713 |  | 70000 | 70000 | 70000 | 89852.45 |  | 350000 | 448122.5289 | 467974.9789
| Total budget | 150000 | 132260 | 17740 |  | 150000 | 202400 | 234935.19 | -84935.19 |  | 150000 | 170000 | 167846.46 | 2153.54 |  | 150000 | 150000 | 155791 | -5791 | 150000 | 203000 | 203000 | 226553.45 | -53000 | 750000 | 893832.65 | 917386.1 | -23553.45 | -3.14%
4. | Planning, Monitoring & Evaluation
| Internal PME capacity | 40000 | 40000 |  |  | 40000 | 41200 | 16353.4798 |  |  | 40000 | 40000 | 48986 |  |  | 40000 | 50000 | 24504.2 |  | 40000 | 50000 | 50000 | 37626.55 |  | 200000 | 179843.6798 | 167470.2298
| Final programme evaluation | [9 empty] | 0 | 120000 | 97265.16 |  |  | 180000 | 60000 | 0 |  |  | 75000 | 75000 | 81917 |  | 180000 | 172265.16 | 179182.16
| Capacity building country PME | 100000 | 29955.4 |  |  | 100000 | 100000 | 39692.9122 |  |  | 100000 | 75000 | 61710.84 |  |  | 100000 | 138000 | 91448 |  | 100000 | 119000 | 119000 | 122724 |  | 500000 | 341807.1522 | 345531.1522
| IATI implementation | 25000 | 4000 |  |  | 25000 | 25000 | 9923.228 |  |  | 25000 | 25000 | 3277.17 |  |  | 25000 | 93000 | 89649.25 |  | 25000 | 25000 | 25000 | 10069.4 |  | 125000 | 131849.648 | 116919.048
| Total budget | 165000 | 73955.4 | 91044.6 |  | 165000 | 166200 | 65969.62 | 99030.38 |  | 165000 | 260000 | 211239.17 | 48760.83 |  | 345000 | 341000 | 205601.45 | 135398.55 | 165000 | 269000 | 269000 | 252336.95 | -104000 | 1005000 | 825765.64 | 809102.59 | 16663.05 | 1.658%
5. | Coordination
| Internal Coordination capacity | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 0 | 25000 | 21952.1251 |  |  | 0 | 21000 | 40248 |  | 0 | 25000 | 25000 | 29293 |  | 0 | 87200.1251 | 91493.1251
| Total budget | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 25000 | 21952.1251 |  |  | 0 | 21000 | 40248 |  | 0 | 25000 | 25000 | 29293 | -25000 | 0 | 87200.1251 | 91493.1251
Total budget Institutional Development |  | 315000 | 206215.4 | 108784.6 |  | 315000 | 368600 | 300904.81 | 14095.19 |  | 315000 | 455000 | 401037.7551 | 53962.2449 |  | 495000 | 512000 | 401640.45 | 110359.55 | 315000 | 497000 | 497000 | 508183.4 | -182000 | 1755000 | 1806798.4151 | 1817981.8151 | -11183.4 | -0.6372%
III - | Programme overhead
| Overhead & office running cost (12%) | 340000 | 222186.72 |  |  | 340000 | 360000 | 311501.4229 |  |  | 340000 | 387740.3329 | 323535.8659 |  |  | 340000 | 474409.1553 | 373954.1129 |  | 340000 | 421880.5919 | 435919.1638 | 348298.9811 |  | 1700000 | 1667097.2854 | 1579477.1027
| Sustainbility budget | [20 empty] | 325523.4945 | 57528.5 |  |  | 325523.4945 | 57528.5
| Audit | 20000 | 10000 |  |  | 20000 | 20000 |  |  |  | 20000 | 20000 | 20045 |  |  | 20000 | 20000 | 20262.55 |  | 20000 | 20000 | 20000 | 20000 |  | 100000 | 70307.55 | 70307.55
|  | 360000 | 232186.72 | 127813.28 |  | 360000 | 380000 | 311501.4229 | 48498.5771 |  | 360000 | 407740.3329 | 343580.8659 | 64159.467 |  | 360000 | 494409.1553 | 394216.6629 | 100192.4924 | 360000 | 441880.5919 | 781442.6582 | 425827.4811 | -81880.5919 | 1800000 | 2062928.3299 | 1707313.1527 | 355615.1772 | 19.76%
Total DfS Budget |  | 2843468.9242 | 2073743.06 | 769725.8642 |  | 2919428.7543 | 3264282.5416 | 2635910.0529 | 283518.7014 |  | 2990188.0966 | 3421702.2489 | 2855115.411 | 135072.6856 |  | 3224185.3835 | 4183628.5086 | 3300042.6329 | -75857.2494 | 3023958.8866 | 3738002.9086 | 4162190.2754 | 3073643.1211 | -714044.022 | 15001230.0451 | 15027001.4322 | 13938454.2778 | 1088547.1543 | 7.256%
|  | 2503468.9242 | 1851556.34 |  | 0 | 2579428.7543 | 2904282.5416 | 2324408.63 |  | 0 | 2650188.0966 | 3033961.916 | 2531579.5451 |  | 0 | 2884185.3835 | 3709219.3533 | 2926088.52 |  | 2683958.8866 | 3316122.3167 | 3726271.1116 |  |  | 13301230.0451 | 13034380.6523 | 12301448.6751
[26 empty] | 1667097.2854 | 14250000
-311545.7222