FIPP: achieved Indicators 2024

| Pathway | Outcome / Intermediate Outcomes | OH/Indicator | Targets | Achieved/2023 | Data collection method |
| --- | --- | --- | --- | --- | --- |
| Pathway 1 | 1. Political parties have strengthened capacity to meaningfully engage the public in political and electoral processes | Outcome Harvesting |  |  | OH workshop |
|  | 1.1 Strategic plans for capacity strengthening in the areas of political programme development, internal democracy and organizational development are set up | # of strategic plans developed | 10 | 10 strategic plans and political programmes developed by 10 political parties | Project documents and party documentation |
|  | 1.2 Political parties develop, distribute and campaign based on responsive political party programmes | # inclusive political party programmes distributed | 10 | 10 political parties disseminated their political programmes at provincial level | Project documents and party documentation |
|  | 1.3 Political parties set up/strengthen consultation and coordination structures | # of political parties with established internal consultation and coordination | 10 | 6 political parties attend consultation workshops in 5 provinces to sensitize their members for more responsibility and consultation on the ground | Party documentation |
| Pathway 2 | 2. Dialogue frameworks between political parties and the Burundian government on peaceful political and electoral processes. | Outcome Harvesting |  |  | OH workshop |
|  | 2.1 Dialogues among political actors and with the Burundian government take place regularly | # of political actor dialogue meetings (at national level) | 9 | 1 political dialogue (national colloque) organized with 63 political actors from inside and outside the country including 19 women and 44 men 1 political dialogue between political actors including CENI to discuss the progress of electoral process and its challenges | Project documents and party documentation |
|  | 2.2 Participating actors have the skills, knowledge and ideas to dialogue meaningfully on political and electoral issues | # of representatives (male/female) of political actors have participated in dialogue oriented training activities) | 300 | 515 actors including youth political leaders discuss governance and the electoral process with the President of Republic | Project documents/activity records |
|  | 2.3 The voices of young men and women in politics and citizens are represented in the various multistakeholder dialogue meetings | # of various dialogue meetings (at national province and commune level) in which young men and women are represented | 17 | 12 dialogue sessions organized at provincial level to discuss youth and women inclusion, prevention against manipulation and electoral violence and sociopolitical issues in their communities | Project documents/activity records |
| Pathway 3 | 3. Young women and men have more capacity, space and voice to engage political actors and political parties on key socio-economic, political and electoral issues | Outcome Harvesting |  |  | OH workshops |
|  | 3.1 More aspiring young (men and women) politicians are actively engaged in politics at all levels | # of youth involved in politics who feel they are able to participate in decision-making processes | 150 | 80 young men and women are supported to strengthen their autonomy, increase their political participation and develop a model of social cohesion | Survey among young people targeted by the programme |
|  | 3.2 Internal intergenerational dialogue with political parties takes place with increased levels participation by young men and women | # of inter-generational dialogue meetings (at national. province and commune level) | 30 | 5 intergenerational dialogue session organized at provincial level including 275 participants (91 women-184 men) | Project documents/activity records |
| Pathway 4 | 4. Programme and policy design capacity of NIMD/BLTP and their international partners reinforced | Outcome Harvesting |  |  | OH workshops |
|  | 4.1 NIMD and partners regularly share and coordinate their interventions and analyses with international stakeholders | # consultations: with representatives of the international community on activities of the project and any progress made or challenged faced regarding interparty dialogue | 6 | 3 meetings organized by the project steering committee on activities of the project and analyze the challenges encountered and find solutions | Project documents/activity records |
|  | 4.2 NIMD and partners (BLTP, RNE) develop in depth understanding of the evolving political landscape towards the 2025 and 2027 elections | # of research notes and analyses on specific topics of interest to the political and electoral process | 9 | 2 research notes and analyses were produced on sociopolitical and electoral context at the eve of 2025 legislative and local elections. | Project documents |
|  | 4.3 Implementing capacity for local implementing partners are ensured | # of funding agreements, including budgets for coordination and learning, signed with local partners | 3 | 7 funding agreements were signed and implemented with 6 local organizations for projects related to political dialogue, women and youth inclusion, prevention of political manipulation and electoral violence, intergenerational dialogue. 4 coordination meetings with held with all the partners. | Project documents |